## KEY
Projects | Sub Color | Subcontractors | Capacity | Scope 1 | Scope 2 | Scope 3 | Scope 4 | Scope 5 | Scope 6 | Scope 7
1 |  | 3C Concrete | 1 | Footer | Slab | Driveway
2 |  | Willett & Assoc. |  | Estimate | Clearing | Site Prep | Rough grade | Rock work
3 |  | Julio H |  | Block | Brick | Stone
4 |  | Gerardo |  | Framing | Siding
|  | Rod Smith |  | Roofing
|  | Dave Kaler |  | Electrical Pre | Electrical Rough | Electrical Finish | Appliances
|  | Adco |  | HVAC Pre | HVAC Rough | HVAC Finish
|  | Hays | 1 | Plumbing Pre | Plumbing Rough | Plumbing Finish
|  | LW Contracting |  | Flooring | Tile Work
|  | Tyler Champion |  | Insulation Block | Insulation Walls | Insulation Ceiling
|  | Bernall Constr. |  | Sheetrock
|  | Danny Liedecher |  | Garage Doors
|  | BlueGrass Gutters |  | Gutters
|  | Matt Thorne | 1 | Trim Interior | Trim Exterior
|  | L&L Painting |  | Painting Primer | Painting Main | Painting Finish
|  | Whittmer |  | Cabinets
|  | Tate Granit |  | Countertops
|  | Angie Mullens |  | Closets
|  | Jacob Hayden |  | Landscaping | Finish Grade | French Drain | Gutter Drains
|  | Ramiro |  | Irrigation
|  | TruGreen |  | Lawn Seeding
|  | Angies Cleaning |  | Cleaning

## Gantt
[7 empty] | 2026-04-05 | [6 empty] | 2026-04-12 | [6 empty] | 2026-04-19 | [6 empty] | 2026-04-26 | [6 empty] | 2026-05-03 | [6 empty] | 2026-05-10 | [6 empty] | 2026-05-17 | [6 empty] | 2026-05-24 | [6 empty] | 2026-05-31 | [6 empty] | 2026-06-07 | [6 empty] | 2026-06-14 | [6 empty] | 2026-06-21 | [6 empty] | 2026-06-28 | [6 empty] | 2026-07-05 | [6 empty] | 2026-07-12 | [6 empty] | 2026-07-19 | [6 empty] | 2026-07-26 | [6 empty] | 2026-08-02 | [6 empty] | 2026-08-09 | [6 empty] | 2026-08-16 | [6 empty] | 2026-08-23 | [6 empty] | 2026-08-30 | [6 empty] | 2026-09-06 | [6 empty] | 2026-09-13 | [6 empty] | 2026-09-20 | [6 empty] | 2026-09-27 | [6 empty] | 2026-10-04 | [6 empty] | 2026-10-11 | [6 empty] | 2026-10-18 | [6 empty] | 2026-10-25 | [6 empty] | 2026-11-01 | [6 empty] | 2026-11-08 | [6 empty] | 2026-11-15 | [6 empty] | 2026-11-22 | [6 empty] | 2026-11-29 | [6 empty] | 2026-12-06 | [6 empty] | 2026-12-13 | [6 empty] | 2026-12-20 | [6 empty] | 2026-12-27 | [6 empty] | 2027-01-03 | [6 empty] | 2027-01-10 | [6 empty] | 2027-01-17 | [6 empty] | 2027-01-24 | [6 empty] | 2027-01-31 | [6 empty] | 2027-02-07 | [6 empty] | 2027-02-14 | [6 empty] | 2027-02-21 | [6 empty] | 2027-02-28 | [6 empty] | 2027-03-07 | [6 empty] | 2027-03-14 | [6 empty] | 2027-03-21
|  |  |  | Days |  |  | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S
Project | Subcontractor | Scope | Start Date | To Complete | End Date | Dependancy | time axis 2026-03-30 to 2027-03-21
IW10 |  | Estimate | 2026-04-01 | 10 | 2026-04-14
|  | Clearing | 2026-04-15 | 3 | 2026-04-17 | Estimate
|  | Site Prep | 2026-04-18 | 2 | 2026-04-20 | Clearing
|  | Footer | 2026-04-21 | 4 | 2026-04-24 | Site Prep
|  | Block | 2026-04-25 | 10 | 2026-05-07 | Footer
|  | French Drain | 2026-05-08 | 2 | 2026-05-11 | Block
|  | Insulation Block | 2026-05-08 | 2 | 2026-05-11 | Block
|  | Rock Work | 2026-05-12 | 2 | 2026-05-13 | Insulation Block
|  | HVAC Pre | 2026-05-14 | 2 | 2026-05-15 | Rock Work
|  | Plumbing Pre | 2026-05-14 | 5 | 2026-05-20 | Rock Work
|  | Electrical Pre | 2026-05-14 | 2 | 2026-05-15 | Rock Work
|  | Slab | 2026-05-21 | 4 | 2026-05-26 | Plumbing Pre
|  | Framing | 2026-05-27 | 30 | 2026-07-07 | Slab
|  | Roofing | 2026-07-08 | 4 | 2026-07-13 | Framing
|  | Brick | 2026-07-14 | 20 | 2026-08-10 | Roofing
|  | Stone | 2026-07-14 | 20 | 2026-08-10 | Roofing
|  | Siding | 2026-07-14 | 20 | 2026-08-10 | Roofing
|  | Rough Grade | 2026-08-11 | 2 | 2026-08-12 | Brick
|  | Irrigation | 2026-08-13 | 2 | 2026-08-14 | Rough Grade
|  | Finish Grade | 2026-08-15 | 2 | 2026-08-17 | Irrigation
|  | Landscaping | 2026-08-15 | 2 | 2026-08-17 | Irrigation
|  | Lawn Seeding | 2026-08-18 | 2 | 2026-08-19 | Finish Grade
|  | Gutter drains | 2026-08-13 | 2 | 2026-08-14 | Rough Grade
|  | HVAC Rough | 2026-07-08 | 5 | 2026-07-14 | Framing
|  | Plumbing Rough | 2026-07-08 | 5 | 2026-07-14 | Framing
|  | Electrical Rough | 2026-07-08 | 10 | 2026-07-21 | Framing
|  | Insulation Walls | 2026-07-22 | 2 | 2026-07-23 | Electrical Rough
|  | Sheetrock | 2026-07-24 | 15 | 2026-08-13 | Insulation Walls
|  | Painting Primer | 2026-08-14 | 3 | 2026-08-18 | Sheetrock
|  | Garage Doors | 2026-08-19 | 2 | 2026-08-20 | Painting Primer
|  | Flooring | 2026-08-19 | 5 | 2026-08-25 | Painting Primer
|  | Tile Work | 2026-08-19 | 8 | 2026-08-28 | Painting Primer
|  | Trim Interior | 2026-08-26 | 20 | 2026-09-22 | Flooring
|  | Trim Exterior | 2026-08-11 | 2 | 2026-08-12 | Siding
|  | Cabinets | 2026-08-26 | 3 | 2026-08-28 | Flooring
|  | Countertops | 2026-08-29 | 2 | 2026-08-31 | Cabinets
|  | Painting Main | 2026-09-01 | 10 | 2026-09-14 | Countertops
|  | Appliances | 2026-09-01 | 2 | 2026-09-02 | Countertops
|  | HVAC Finish | 2026-09-15 | 2 | 2026-09-16 | Painting Main
|  | Plumbing Finish | 2026-09-01 | 2 | 2026-09-02 | Countertops
|  | Electrical Finish | 2026-09-15 | 4 | 2026-09-18 | Painting Main
|  | Insulation Ceiling | 2026-09-19 | 2 | 2026-09-21 | Electrical Finish
|  | Painting Finish | 2026-09-19 | 5 | 2026-09-24 | Electrical Finish
|  | Cleaning | 2026-09-25 | 3 | 2026-09-29 | Painting Finish
|  |  |  | 181 | Estimate to cleaning
|  |  |  | 167 | Days to build
|  |  |  | 5.4916 | Months to build

## Projects
Project | Start Date | Notes | How to use
IW10 | 2026-04-01 | Base project from original schedule | 1) Edit project start dates here.
IW11 | 2026-04-22 | Edit this start date | 2) Edit task durations in Schedule Engine column K.
IW12 | 2026-05-13 | Edit this start date | 3) Calculated Start/Finish update automatically.
IW13 | 2026-06-03 | Future slot | 4) Red bars/load cells mean bottleneck delay or overlap risk.
IW14 | 2026-06-24 | Future slot
IW15 | 2026-07-15 | Future slot

## Task Template
Task Order | Scope | Subcontractor | Default Days | Dependency | Bottleneck Vendor
1 | Estimate | Willett & Assoc. | 10
2 | Clearing | Willett & Assoc. | 3 | Estimate
3 | Site Prep | Willett & Assoc. | 2 | Clearing
4 | Footer | 3C Concrete | 4 | Site Prep | 3C Concrete
5 | Block | Julio H | 10 | Footer
6 | French Drain | Jacob Hayden | 2 | Block
7 | Insulation Block | Tyler Champion | 2 | Block
8 | Rock Work |  | 2 | Insulation Block
9 | HVAC Pre | Adco | 2 | Rock Work
10 | Plumbing Pre | Hays | 5 | Rock Work | Hays
11 | Electrical Pre | Dave Kaler | 2 | Rock Work
12 | Slab | 3C Concrete | 4 | Plumbing Pre | 3C Concrete
13 | Framing | Gerardo | 30 | Slab
14 | Roofing | Rod Smith | 4 | Framing
15 | Brick | Julio H | 20 | Roofing
16 | Stone | Julio H | 20 | Roofing
17 | Siding | Gerardo | 20 | Roofing
18 | Rough Grade |  | 2 | Brick
19 | Irrigation | Ramiro | 2 | Rough Grade
20 | Finish Grade | Jacob Hayden | 2 | Irrigation
21 | Landscaping | Jacob Hayden | 2 | Irrigation
22 | Lawn Seeding | TruGreen | 2 | Finish Grade
23 | Gutter drains |  | 2 | Rough Grade
24 | HVAC Rough | Adco | 5 | Framing
25 | Plumbing Rough | Hays | 5 | Framing | Hays
26 | Electrical Rough | Dave Kaler | 10 | Framing
27 | Insulation Walls | Tyler Champion | 2 | Electrical Rough
28 | Sheetrock | Bernall Constr. | 15 | Insulation Walls
29 | Painting Primer | L&L Painting | 3 | Sheetrock
30 | Garage Doors | Danny Liedecher | 2 | Painting Primer
31 | Flooring | LW Contracting | 5 | Painting Primer
32 | Tile Work | LW Contracting | 8 | Painting Primer
33 | Trim Interior | Matt Thorne | 20 | Flooring | Matt Thorne
34 | Trim Exterior | Matt Thorne | 2 | Siding | Matt Thorne
35 | Cabinets | Whittmer | 3 | Flooring
36 | Countertops | Tate Granit | 2 | Cabinets
37 | Painting Main | L&L Painting | 10 | Countertops
38 | Appliances | Dave Kaler | 2 | Countertops
39 | HVAC Finish | Adco | 2 | Painting Main
40 | Plumbing Finish | Hays | 2 | Countertops | Hays
41 | Electrical Finish | Dave Kaler | 4 | Painting Main
42 | Insulation Ceiling | Tyler Champion | 2 | Electrical Finish
43 | Painting Finish | L&L Painting | 5 | Electrical Finish
44 | Cleaning | Angies Cleaning | 3 | Painting Finish

## Schedule Engine
Seq | Project | Project Start | Task Order | Scope | Subcontractor | Bottleneck Vendor | Dependency | Task Key | Dependency Key | Days | Logic Start | Prev Bottleneck Finish | Calculated Start | Calculated Finish | Delay Days | Status
1 | IW10 | 2026-04-01 | 1 | Estimate | Willett & Assoc. |  |  | IW10¦Estimate |  | 10 | 2026-04-01 |  | 2026-04-01 | 2026-04-14 | 0
2 | IW10 | 2026-04-01 | 2 | Clearing | Willett & Assoc. |  | Estimate | IW10¦Clearing | IW10¦Estimate | 3 | 2026-04-15 |  | 2026-04-15 | 2026-04-17 | 0
3 | IW10 | 2026-04-01 | 3 | Site Prep | Willett & Assoc. |  | Clearing | IW10¦Site Prep | IW10¦Clearing | 2 | 2026-04-20 |  | 2026-04-20 | 2026-04-21 | 0
4 | IW10 | 2026-04-01 | 4 | Footer | 3C Concrete | 3C Concrete | Site Prep | IW10¦Footer | IW10¦Site Prep | 4 | 2026-04-22 |  | 2026-04-22 | 2026-04-27 | 0
5 | IW10 | 2026-04-01 | 5 | Block | Julio H |  | Footer | IW10¦Block | IW10¦Footer | 10 | 2026-04-28 |  | 2026-04-28 | 2026-05-11 | 0
6 | IW10 | 2026-04-01 | 6 | French Drain | Jacob Hayden |  | Block | IW10¦French Drain | IW10¦Block | 2 | 2026-05-12 |  | 2026-05-12 | 2026-05-13 | 0
7 | IW10 | 2026-04-01 | 7 | Insulation Block | Tyler Champion |  | Block | IW10¦Insulation Block | IW10¦Block | 2 | 2026-05-12 |  | 2026-05-12 | 2026-05-13 | 0
8 | IW10 | 2026-04-01 | 8 | Rock Work |  |  | Insulation Block | IW10¦Rock Work | IW10¦Insulation Block | 2 | 2026-05-14 |  | 2026-05-14 | 2026-05-15 | 0
9 | IW10 | 2026-04-01 | 9 | HVAC Pre | Adco |  | Rock Work | IW10¦HVAC Pre | IW10¦Rock Work | 2 | 2026-05-18 |  | 2026-05-18 | 2026-05-19 | 0
10 | IW10 | 2026-04-01 | 10 | Plumbing Pre | Hays | Hays | Rock Work | IW10¦Plumbing Pre | IW10¦Rock Work | 5 | 2026-05-18 |  | 2026-05-18 | 2026-05-22 | 0
11 | IW10 | 2026-04-01 | 11 | Electrical Pre | Dave Kaler |  | Rock Work | IW10¦Electrical Pre | IW10¦Rock Work | 2 | 2026-05-18 |  | 2026-05-18 | 2026-05-19 | 0
12 | IW10 | 2026-04-01 | 12 | Slab | 3C Concrete | 3C Concrete | Plumbing Pre | IW10¦Slab | IW10¦Plumbing Pre | 4 | 2026-05-25 |  | 2026-05-25 | 2026-05-28 | 0
13 | IW10 | 2026-04-01 | 13 | Framing | Gerardo |  | Slab | IW10¦Framing | IW10¦Slab | 30 | 2026-05-29 |  | 2026-05-29 | 2026-07-09 | 0
14 | IW10 | 2026-04-01 | 14 | Roofing | Rod Smith |  | Framing | IW10¦Roofing | IW10¦Framing | 4 | 2026-07-10 |  | 2026-07-10 | 2026-07-15 | 0
15 | IW10 | 2026-04-01 | 15 | Brick | Julio H |  | Roofing | IW10¦Brick | IW10¦Roofing | 20 | 2026-07-16 |  | 2026-07-16 | 2026-08-12 | 0
16 | IW10 | 2026-04-01 | 16 | Stone | Julio H |  | Roofing | IW10¦Stone | IW10¦Roofing | 20 | 2026-07-16 |  | 2026-07-16 | 2026-08-12 | 0
17 | IW10 | 2026-04-01 | 17 | Siding | Gerardo |  | Roofing | IW10¦Siding | IW10¦Roofing | 20 | 2026-07-16 |  | 2026-07-16 | 2026-08-12 | 0
18 | IW10 | 2026-04-01 | 18 | Rough Grade |  |  | Brick | IW10¦Rough Grade | IW10¦Brick | 2 | 2026-08-13 |  | 2026-08-13 | 2026-08-14 | 0
19 | IW10 | 2026-04-01 | 19 | Irrigation | Ramiro |  | Rough Grade | IW10¦Irrigation | IW10¦Rough Grade | 2 | 2026-08-17 |  | 2026-08-17 | 2026-08-18 | 0
20 | IW10 | 2026-04-01 | 20 | Finish Grade | Jacob Hayden |  | Irrigation | IW10¦Finish Grade | IW10¦Irrigation | 2 | 2026-08-19 |  | 2026-08-19 | 2026-08-20 | 0
21 | IW10 | 2026-04-01 | 21 | Landscaping | Jacob Hayden |  | Irrigation | IW10¦Landscaping | IW10¦Irrigation | 2 | 2026-08-19 |  | 2026-08-19 | 2026-08-20 | 0
22 | IW10 | 2026-04-01 | 22 | Lawn Seeding | TruGreen |  | Finish Grade | IW10¦Lawn Seeding | IW10¦Finish Grade | 2 | 2026-08-21 |  | 2026-08-21 | 2026-08-24 | 0
23 | IW10 | 2026-04-01 | 23 | Gutter drains |  |  | Rough Grade | IW10¦Gutter drains | IW10¦Rough Grade | 2 | 2026-08-17 |  | 2026-08-17 | 2026-08-18 | 0
24 | IW10 | 2026-04-01 | 24 | HVAC Rough | Adco |  | Framing | IW10¦HVAC Rough | IW10¦Framing | 5 | 2026-07-10 |  | 2026-07-10 | 2026-07-16 | 0
25 | IW10 | 2026-04-01 | 25 | Plumbing Rough | Hays | Hays | Framing | IW10¦Plumbing Rough | IW10¦Framing | 5 | 2026-07-10 |  | 2026-07-10 | 2026-07-16 | 0
26 | IW10 | 2026-04-01 | 26 | Electrical Rough | Dave Kaler |  | Framing | IW10¦Electrical Rough | IW10¦Framing | 10 | 2026-07-10 |  | 2026-07-10 | 2026-07-23 | 0
27 | IW10 | 2026-04-01 | 27 | Insulation Walls | Tyler Champion |  | Electrical Rough | IW10¦Insulation Walls | IW10¦Electrical Rough | 2 | 2026-07-24 |  | 2026-07-24 | 2026-07-27 | 0
28 | IW10 | 2026-04-01 | 28 | Sheetrock | Bernall Constr. |  | Insulation Walls | IW10¦Sheetrock | IW10¦Insulation Walls | 15 | 2026-07-28 |  | 2026-07-28 | 2026-08-17 | 0
29 | IW10 | 2026-04-01 | 29 | Painting Primer | L&L Painting |  | Sheetrock | IW10¦Painting Primer | IW10¦Sheetrock | 3 | 2026-08-18 |  | 2026-08-18 | 2026-08-20 | 0
30 | IW10 | 2026-04-01 | 30 | Garage Doors | Danny Liedecher |  | Painting Primer | IW10¦Garage Doors | IW10¦Painting Primer | 2 | 2026-08-21 |  | 2026-08-21 | 2026-08-24 | 0
31 | IW10 | 2026-04-01 | 31 | Flooring | LW Contracting |  | Painting Primer | IW10¦Flooring | IW10¦Painting Primer | 5 | 2026-08-21 |  | 2026-08-21 | 2026-08-27 | 0
32 | IW10 | 2026-04-01 | 32 | Tile Work | LW Contracting |  | Painting Primer | IW10¦Tile Work | IW10¦Painting Primer | 8 | 2026-08-21 |  | 2026-08-21 | 2026-09-01 | 0
33 | IW10 | 2026-04-01 | 33 | Trim Interior | Matt Thorne | Matt Thorne | Flooring | IW10¦Trim Interior | IW10¦Flooring | 20 | 2026-08-28 |  | 2026-08-28 | 2026-09-24 | 0
34 | IW10 | 2026-04-01 | 34 | Trim Exterior | Matt Thorne | Matt Thorne | Siding | IW10¦Trim Exterior | IW10¦Siding | 2 | 2026-08-13 |  | 2026-08-13 | 2026-08-14 | 0
35 | IW10 | 2026-04-01 | 35 | Cabinets | Whittmer |  | Flooring | IW10¦Cabinets | IW10¦Flooring | 3 | 2026-08-28 |  | 2026-08-28 | 2026-09-01 | 0
36 | IW10 | 2026-04-01 | 36 | Countertops | Tate Granit |  | Cabinets | IW10¦Countertops | IW10¦Cabinets | 2 | 2026-09-02 |  | 2026-09-02 | 2026-09-03 | 0
37 | IW10 | 2026-04-01 | 37 | Painting Main | L&L Painting |  | Countertops | IW10¦Painting Main | IW10¦Countertops | 10 | 2026-09-04 |  | 2026-09-04 | 2026-09-17 | 0
38 | IW10 | 2026-04-01 | 38 | Appliances | Dave Kaler |  | Countertops | IW10¦Appliances | IW10¦Countertops | 2 | 2026-09-04 |  | 2026-09-04 | 2026-09-07 | 0
39 | IW10 | 2026-04-01 | 39 | HVAC Finish | Adco |  | Painting Main | IW10¦HVAC Finish | IW10¦Painting Main | 2 | 2026-09-18 |  | 2026-09-18 | 2026-09-21 | 0
40 | IW10 | 2026-04-01 | 40 | Plumbing Finish | Hays | Hays | Countertops | IW10¦Plumbing Finish | IW10¦Countertops | 2 | 2026-09-04 |  | 2026-09-04 | 2026-09-07 | 0
41 | IW10 | 2026-04-01 | 41 | Electrical Finish | Dave Kaler |  | Painting Main | IW10¦Electrical Finish | IW10¦Painting Main | 4 | 2026-09-18 |  | 2026-09-18 | 2026-09-23 | 0
42 | IW10 | 2026-04-01 | 42 | Insulation Ceiling | Tyler Champion |  | Electrical Finish | IW10¦Insulation Ceiling | IW10¦Electrical Finish | 2 | 2026-09-24 |  | 2026-09-24 | 2026-09-25 | 0
43 | IW10 | 2026-04-01 | 43 | Painting Finish | L&L Painting |  | Electrical Finish | IW10¦Painting Finish | IW10¦Electrical Finish | 5 | 2026-09-24 |  | 2026-09-24 | 2026-09-30 | 0
44 | IW10 | 2026-04-01 | 44 | Cleaning | Angies Cleaning |  | Painting Finish | IW10¦Cleaning | IW10¦Painting Finish | 3 | 2026-10-01 |  | 2026-10-01 | 2026-10-05 | 0
45 | IW11 | 2026-04-22 | 1 | Estimate | Willett & Assoc. |  |  | IW11¦Estimate |  | 10 | 2026-04-22 |  | 2026-04-22 | 2026-05-05 | 0
46 | IW11 | 2026-04-22 | 2 | Clearing | Willett & Assoc. |  | Estimate | IW11¦Clearing | IW11¦Estimate | 3 | 2026-05-06 |  | 2026-05-06 | 2026-05-08 | 0
47 | IW11 | 2026-04-22 | 3 | Site Prep | Willett & Assoc. |  | Clearing | IW11¦Site Prep | IW11¦Clearing | 2 | 2026-05-11 |  | 2026-05-11 | 2026-05-12 | 0
48 | IW11 | 2026-04-22 | 4 | Footer | 3C Concrete | 3C Concrete | Site Prep | IW11¦Footer | IW11¦Site Prep | 4 | 2026-05-13 |  | 2026-05-13 | 2026-05-18 | 0
49 | IW11 | 2026-04-22 | 5 | Block | Julio H |  | Footer | IW11¦Block | IW11¦Footer | 10 | 2026-05-19 |  | 2026-05-19 | 2026-06-01 | 0
50 | IW11 | 2026-04-22 | 6 | French Drain | Jacob Hayden |  | Block | IW11¦French Drain | IW11¦Block | 2 | 2026-06-02 |  | 2026-06-02 | 2026-06-03 | 0
51 | IW11 | 2026-04-22 | 7 | Insulation Block | Tyler Champion |  | Block | IW11¦Insulation Block | IW11¦Block | 2 | 2026-06-02 |  | 2026-06-02 | 2026-06-03 | 0
52 | IW11 | 2026-04-22 | 8 | Rock Work |  |  | Insulation Block | IW11¦Rock Work | IW11¦Insulation Block | 2 | 2026-06-04 |  | 2026-06-04 | 2026-06-05 | 0
53 | IW11 | 2026-04-22 | 9 | HVAC Pre | Adco |  | Rock Work | IW11¦HVAC Pre | IW11¦Rock Work | 2 | 2026-06-08 |  | 2026-06-08 | 2026-06-09 | 0
54 | IW11 | 2026-04-22 | 10 | Plumbing Pre | Hays | Hays | Rock Work | IW11¦Plumbing Pre | IW11¦Rock Work | 5 | 2026-06-08 |  | 2026-06-08 | 2026-06-12 | 0
55 | IW11 | 2026-04-22 | 11 | Electrical Pre | Dave Kaler |  | Rock Work | IW11¦Electrical Pre | IW11¦Rock Work | 2 | 2026-06-08 |  | 2026-06-08 | 2026-06-09 | 0
56 | IW11 | 2026-04-22 | 12 | Slab | 3C Concrete | 3C Concrete | Plumbing Pre | IW11¦Slab | IW11¦Plumbing Pre | 4 | 2026-06-15 |  | 2026-06-15 | 2026-06-18 | 0
57 | IW11 | 2026-04-22 | 13 | Framing | Gerardo |  | Slab | IW11¦Framing | IW11¦Slab | 30 | 2026-06-19 |  | 2026-06-19 | 2026-07-30 | 0
58 | IW11 | 2026-04-22 | 14 | Roofing | Rod Smith |  | Framing | IW11¦Roofing | IW11¦Framing | 4 | 2026-07-31 |  | 2026-07-31 | 2026-08-05 | 0
59 | IW11 | 2026-04-22 | 15 | Brick | Julio H |  | Roofing | IW11¦Brick | IW11¦Roofing | 20 | 2026-08-06 |  | 2026-08-06 | 2026-09-02 | 0
60 | IW11 | 2026-04-22 | 16 | Stone | Julio H |  | Roofing | IW11¦Stone | IW11¦Roofing | 20 | 2026-08-06 |  | 2026-08-06 | 2026-09-02 | 0
61 | IW11 | 2026-04-22 | 17 | Siding | Gerardo |  | Roofing | IW11¦Siding | IW11¦Roofing | 20 | 2026-08-06 |  | 2026-08-06 | 2026-09-02 | 0
62 | IW11 | 2026-04-22 | 18 | Rough Grade |  |  | Brick | IW11¦Rough Grade | IW11¦Brick | 2 | 2026-09-03 |  | 2026-09-03 | 2026-09-04 | 0
63 | IW11 | 2026-04-22 | 19 | Irrigation | Ramiro |  | Rough Grade | IW11¦Irrigation | IW11¦Rough Grade | 2 | 2026-09-07 |  | 2026-09-07 | 2026-09-08 | 0
64 | IW11 | 2026-04-22 | 20 | Finish Grade | Jacob Hayden |  | Irrigation | IW11¦Finish Grade | IW11¦Irrigation | 2 | 2026-09-09 |  | 2026-09-09 | 2026-09-10 | 0
65 | IW11 | 2026-04-22 | 21 | Landscaping | Jacob Hayden |  | Irrigation | IW11¦Landscaping | IW11¦Irrigation | 2 | 2026-09-09 |  | 2026-09-09 | 2026-09-10 | 0
66 | IW11 | 2026-04-22 | 22 | Lawn Seeding | TruGreen |  | Finish Grade | IW11¦Lawn Seeding | IW11¦Finish Grade | 2 | 2026-09-11 |  | 2026-09-11 | 2026-09-14 | 0
67 | IW11 | 2026-04-22 | 23 | Gutter drains |  |  | Rough Grade | IW11¦Gutter drains | IW11¦Rough Grade | 2 | 2026-09-07 |  | 2026-09-07 | 2026-09-08 | 0
68 | IW11 | 2026-04-22 | 24 | HVAC Rough | Adco |  | Framing | IW11¦HVAC Rough | IW11¦Framing | 5 | 2026-07-31 |  | 2026-07-31 | 2026-08-06 | 0
69 | IW11 | 2026-04-22 | 25 | Plumbing Rough | Hays | Hays | Framing | IW11¦Plumbing Rough | IW11¦Framing | 5 | 2026-07-31 |  | 2026-07-31 | 2026-08-06 | 0
70 | IW11 | 2026-04-22 | 26 | Electrical Rough | Dave Kaler |  | Framing | IW11¦Electrical Rough | IW11¦Framing | 10 | 2026-07-31 |  | 2026-07-31 | 2026-08-13 | 0
71 | IW11 | 2026-04-22 | 27 | Insulation Walls | Tyler Champion |  | Electrical Rough | IW11¦Insulation Walls | IW11¦Electrical Rough | 2 | 2026-08-14 |  | 2026-08-14 | 2026-08-17 | 0
72 | IW11 | 2026-04-22 | 28 | Sheetrock | Bernall Constr. |  | Insulation Walls | IW11¦Sheetrock | IW11¦Insulation Walls | 15 | 2026-08-18 |  | 2026-08-18 | 2026-09-07 | 0
73 | IW11 | 2026-04-22 | 29 | Painting Primer | L&L Painting |  | Sheetrock | IW11¦Painting Primer | IW11¦Sheetrock | 3 | 2026-09-08 |  | 2026-09-08 | 2026-09-10 | 0
74 | IW11 | 2026-04-22 | 30 | Garage Doors | Danny Liedecher |  | Painting Primer | IW11¦Garage Doors | IW11¦Painting Primer | 2 | 2026-09-11 |  | 2026-09-11 | 2026-09-14 | 0
75 | IW11 | 2026-04-22 | 31 | Flooring | LW Contracting |  | Painting Primer | IW11¦Flooring | IW11¦Painting Primer | 5 | 2026-09-11 |  | 2026-09-11 | 2026-09-17 | 0
76 | IW11 | 2026-04-22 | 32 | Tile Work | LW Contracting |  | Painting Primer | IW11¦Tile Work | IW11¦Painting Primer | 8 | 2026-09-11 |  | 2026-09-11 | 2026-09-22 | 0
77 | IW11 | 2026-04-22 | 33 | Trim Interior | Matt Thorne | Matt Thorne | Flooring | IW11¦Trim Interior | IW11¦Flooring | 20 | 2026-09-18 |  | 2026-09-18 | 2026-10-15 | 0
78 | IW11 | 2026-04-22 | 34 | Trim Exterior | Matt Thorne | Matt Thorne | Siding | IW11¦Trim Exterior | IW11¦Siding | 2 | 2026-09-03 |  | 2026-09-03 | 2026-09-04 | 0
79 | IW11 | 2026-04-22 | 35 | Cabinets | Whittmer |  | Flooring | IW11¦Cabinets | IW11¦Flooring | 3 | 2026-09-18 |  | 2026-09-18 | 2026-09-22 | 0
80 | IW11 | 2026-04-22 | 36 | Countertops | Tate Granit |  | Cabinets | IW11¦Countertops | IW11¦Cabinets | 2 | 2026-09-23 |  | 2026-09-23 | 2026-09-24 | 0
81 | IW11 | 2026-04-22 | 37 | Painting Main | L&L Painting |  | Countertops | IW11¦Painting Main | IW11¦Countertops | 10 | 2026-09-25 |  | 2026-09-25 | 2026-10-08 | 0
82 | IW11 | 2026-04-22 | 38 | Appliances | Dave Kaler |  | Countertops | IW11¦Appliances | IW11¦Countertops | 2 | 2026-09-25 |  | 2026-09-25 | 2026-09-28 | 0
83 | IW11 | 2026-04-22 | 39 | HVAC Finish | Adco |  | Painting Main | IW11¦HVAC Finish | IW11¦Painting Main | 2 | 2026-10-09 |  | 2026-10-09 | 2026-10-12 | 0
84 | IW11 | 2026-04-22 | 40 | Plumbing Finish | Hays | Hays | Countertops | IW11¦Plumbing Finish | IW11¦Countertops | 2 | 2026-09-25 |  | 2026-09-25 | 2026-09-28 | 0
85 | IW11 | 2026-04-22 | 41 | Electrical Finish | Dave Kaler |  | Painting Main | IW11¦Electrical Finish | IW11¦Painting Main | 4 | 2026-10-09 |  | 2026-10-09 | 2026-10-14 | 0
86 | IW11 | 2026-04-22 | 42 | Insulation Ceiling | Tyler Champion |  | Electrical Finish | IW11¦Insulation Ceiling | IW11¦Electrical Finish | 2 | 2026-10-15 |  | 2026-10-15 | 2026-10-16 | 0
87 | IW11 | 2026-04-22 | 43 | Painting Finish | L&L Painting |  | Electrical Finish | IW11¦Painting Finish | IW11¦Electrical Finish | 5 | 2026-10-15 |  | 2026-10-15 | 2026-10-21 | 0
88 | IW11 | 2026-04-22 | 44 | Cleaning | Angies Cleaning |  | Painting Finish | IW11¦Cleaning | IW11¦Painting Finish | 3 | 2026-10-22 |  | 2026-10-22 | 2026-10-26 | 0
89 | IW12 | 2026-05-13 | 1 | Estimate | Willett & Assoc. |  |  | IW12¦Estimate |  | 10 | 2026-05-13 |  | 2026-05-13 | 2026-05-26 | 0
90 | IW12 | 2026-05-13 | 2 | Clearing | Willett & Assoc. |  | Estimate | IW12¦Clearing | IW12¦Estimate | 3 | 2026-05-27 |  | 2026-05-27 | 2026-05-29 | 0
91 | IW12 | 2026-05-13 | 3 | Site Prep | Willett & Assoc. |  | Clearing | IW12¦Site Prep | IW12¦Clearing | 2 | 2026-06-01 |  | 2026-06-01 | 2026-06-02 | 0
92 | IW12 | 2026-05-13 | 4 | Footer | 3C Concrete | 3C Concrete | Site Prep | IW12¦Footer | IW12¦Site Prep | 4 | 2026-06-03 |  | 2026-06-03 | 2026-06-08 | 0
93 | IW12 | 2026-05-13 | 5 | Block | Julio H |  | Footer | IW12¦Block | IW12¦Footer | 10 | 2026-06-09 |  | 2026-06-09 | 2026-06-22 | 0
94 | IW12 | 2026-05-13 | 6 | French Drain | Jacob Hayden |  | Block | IW12¦French Drain | IW12¦Block | 2 | 2026-06-23 |  | 2026-06-23 | 2026-06-24 | 0
95 | IW12 | 2026-05-13 | 7 | Insulation Block | Tyler Champion |  | Block | IW12¦Insulation Block | IW12¦Block | 2 | 2026-06-23 |  | 2026-06-23 | 2026-06-24 | 0
96 | IW12 | 2026-05-13 | 8 | Rock Work |  |  | Insulation Block | IW12¦Rock Work | IW12¦Insulation Block | 2 | 2026-06-25 |  | 2026-06-25 | 2026-06-26 | 0
97 | IW12 | 2026-05-13 | 9 | HVAC Pre | Adco |  | Rock Work | IW12¦HVAC Pre | IW12¦Rock Work | 2 | 2026-06-29 |  | 2026-06-29 | 2026-06-30 | 0
98 | IW12 | 2026-05-13 | 10 | Plumbing Pre | Hays | Hays | Rock Work | IW12¦Plumbing Pre | IW12¦Rock Work | 5 | 2026-06-29 |  | 2026-06-29 | 2026-07-03 | 0
99 | IW12 | 2026-05-13 | 11 | Electrical Pre | Dave Kaler |  | Rock Work | IW12¦Electrical Pre | IW12¦Rock Work | 2 | 2026-06-29 |  | 2026-06-29 | 2026-06-30 | 0
100 | IW12 | 2026-05-13 | 12 | Slab | 3C Concrete | 3C Concrete | Plumbing Pre | IW12¦Slab | IW12¦Plumbing Pre | 4 | 2026-07-06 |  | 2026-07-06 | 2026-07-09 | 0
101 | IW12 | 2026-05-13 | 13 | Framing | Gerardo |  | Slab | IW12¦Framing | IW12¦Slab | 30 | 2026-07-10 |  | 2026-07-10 | 2026-08-20 | 0
102 | IW12 | 2026-05-13 | 14 | Roofing | Rod Smith |  | Framing | IW12¦Roofing | IW12¦Framing | 4 | 2026-08-21 |  | 2026-08-21 | 2026-08-26 | 0
103 | IW12 | 2026-05-13 | 15 | Brick | Julio H |  | Roofing | IW12¦Brick | IW12¦Roofing | 20 | 2026-08-27 |  | 2026-08-27 | 2026-09-23 | 0
104 | IW12 | 2026-05-13 | 16 | Stone | Julio H |  | Roofing | IW12¦Stone | IW12¦Roofing | 20 | 2026-08-27 |  | 2026-08-27 | 2026-09-23 | 0
105 | IW12 | 2026-05-13 | 17 | Siding | Gerardo |  | Roofing | IW12¦Siding | IW12¦Roofing | 20 | 2026-08-27 |  | 2026-08-27 | 2026-09-23 | 0
106 | IW12 | 2026-05-13 | 18 | Rough Grade |  |  | Brick | IW12¦Rough Grade | IW12¦Brick | 2 | 2026-09-24 |  | 2026-09-24 | 2026-09-25 | 0
107 | IW12 | 2026-05-13 | 19 | Irrigation | Ramiro |  | Rough Grade | IW12¦Irrigation | IW12¦Rough Grade | 2 | 2026-09-28 |  | 2026-09-28 | 2026-09-29 | 0
108 | IW12 | 2026-05-13 | 20 | Finish Grade | Jacob Hayden |  | Irrigation | IW12¦Finish Grade | IW12¦Irrigation | 2 | 2026-09-30 |  | 2026-09-30 | 2026-10-01 | 0
109 | IW12 | 2026-05-13 | 21 | Landscaping | Jacob Hayden |  | Irrigation | IW12¦Landscaping | IW12¦Irrigation | 2 | 2026-09-30 |  | 2026-09-30 | 2026-10-01 | 0
110 | IW12 | 2026-05-13 | 22 | Lawn Seeding | TruGreen |  | Finish Grade | IW12¦Lawn Seeding | IW12¦Finish Grade | 2 | 2026-10-02 |  | 2026-10-02 | 2026-10-05 | 0
111 | IW12 | 2026-05-13 | 23 | Gutter drains |  |  | Rough Grade | IW12¦Gutter drains | IW12¦Rough Grade | 2 | 2026-09-28 |  | 2026-09-28 | 2026-09-29 | 0
112 | IW12 | 2026-05-13 | 24 | HVAC Rough | Adco |  | Framing | IW12¦HVAC Rough | IW12¦Framing | 5 | 2026-08-21 |  | 2026-08-21 | 2026-08-27 | 0
113 | IW12 | 2026-05-13 | 25 | Plumbing Rough | Hays | Hays | Framing | IW12¦Plumbing Rough | IW12¦Framing | 5 | 2026-08-21 |  | 2026-08-21 | 2026-08-27 | 0
114 | IW12 | 2026-05-13 | 26 | Electrical Rough | Dave Kaler |  | Framing | IW12¦Electrical Rough | IW12¦Framing | 10 | 2026-08-21 |  | 2026-08-21 | 2026-09-03 | 0
115 | IW12 | 2026-05-13 | 27 | Insulation Walls | Tyler Champion |  | Electrical Rough | IW12¦Insulation Walls | IW12¦Electrical Rough | 2 | 2026-09-04 |  | 2026-09-04 | 2026-09-07 | 0
116 | IW12 | 2026-05-13 | 28 | Sheetrock | Bernall Constr. |  | Insulation Walls | IW12¦Sheetrock | IW12¦Insulation Walls | 15 | 2026-09-08 |  | 2026-09-08 | 2026-09-28 | 0
117 | IW12 | 2026-05-13 | 29 | Painting Primer | L&L Painting |  | Sheetrock | IW12¦Painting Primer | IW12¦Sheetrock | 3 | 2026-09-29 |  | 2026-09-29 | 2026-10-01 | 0
118 | IW12 | 2026-05-13 | 30 | Garage Doors | Danny Liedecher |  | Painting Primer | IW12¦Garage Doors | IW12¦Painting Primer | 2 | 2026-10-02 |  | 2026-10-02 | 2026-10-05 | 0
119 | IW12 | 2026-05-13 | 31 | Flooring | LW Contracting |  | Painting Primer | IW12¦Flooring | IW12¦Painting Primer | 5 | 2026-10-02 |  | 2026-10-02 | 2026-10-08 | 0
120 | IW12 | 2026-05-13 | 32 | Tile Work | LW Contracting |  | Painting Primer | IW12¦Tile Work | IW12¦Painting Primer | 8 | 2026-10-02 |  | 2026-10-02 | 2026-10-13 | 0
121 | IW12 | 2026-05-13 | 33 | Trim Interior | Matt Thorne | Matt Thorne | Flooring | IW12¦Trim Interior | IW12¦Flooring | 20 | 2026-10-09 |  | 2026-10-09 | 2026-11-05 | 0
122 | IW12 | 2026-05-13 | 34 | Trim Exterior | Matt Thorne | Matt Thorne | Siding | IW12¦Trim Exterior | IW12¦Siding | 2 | 2026-09-24 |  | 2026-09-24 | 2026-09-25 | 0
123 | IW12 | 2026-05-13 | 35 | Cabinets | Whittmer |  | Flooring | IW12¦Cabinets | IW12¦Flooring | 3 | 2026-10-09 |  | 2026-10-09 | 2026-10-13 | 0
124 | IW12 | 2026-05-13 | 36 | Countertops | Tate Granit |  | Cabinets | IW12¦Countertops | IW12¦Cabinets | 2 | 2026-10-14 |  | 2026-10-14 | 2026-10-15 | 0
125 | IW12 | 2026-05-13 | 37 | Painting Main | L&L Painting |  | Countertops | IW12¦Painting Main | IW12¦Countertops | 10 | 2026-10-16 |  | 2026-10-16 | 2026-10-29 | 0
126 | IW12 | 2026-05-13 | 38 | Appliances | Dave Kaler |  | Countertops | IW12¦Appliances | IW12¦Countertops | 2 | 2026-10-16 |  | 2026-10-16 | 2026-10-19 | 0
127 | IW12 | 2026-05-13 | 39 | HVAC Finish | Adco |  | Painting Main | IW12¦HVAC Finish | IW12¦Painting Main | 2 | 2026-10-30 |  | 2026-10-30 | 2026-11-02 | 0
128 | IW12 | 2026-05-13 | 40 | Plumbing Finish | Hays | Hays | Countertops | IW12¦Plumbing Finish | IW12¦Countertops | 2 | 2026-10-16 |  | 2026-10-16 | 2026-10-19 | 0
129 | IW12 | 2026-05-13 | 41 | Electrical Finish | Dave Kaler |  | Painting Main | IW12¦Electrical Finish | IW12¦Painting Main | 4 | 2026-10-30 |  | 2026-10-30 | 2026-11-04 | 0
130 | IW12 | 2026-05-13 | 42 | Insulation Ceiling | Tyler Champion |  | Electrical Finish | IW12¦Insulation Ceiling | IW12¦Electrical Finish | 2 | 2026-11-05 |  | 2026-11-05 | 2026-11-06 | 0
131 | IW12 | 2026-05-13 | 43 | Painting Finish | L&L Painting |  | Electrical Finish | IW12¦Painting Finish | IW12¦Electrical Finish | 5 | 2026-11-05 |  | 2026-11-05 | 2026-11-11 | 0
132 | IW12 | 2026-05-13 | 44 | Cleaning | Angies Cleaning |  | Painting Finish | IW12¦Cleaning | IW12¦Painting Finish | 3 | 2026-11-12 |  | 2026-11-12 | 2026-11-16 | 0
133 | IW13 | 2026-06-03 | 1 | Estimate | Willett & Assoc. |  |  | IW13¦Estimate |  | 10 | 2026-06-03 |  | 2026-06-03 | 2026-06-16 | 0
134 | IW13 | 2026-06-03 | 2 | Clearing | Willett & Assoc. |  | Estimate | IW13¦Clearing | IW13¦Estimate | 3 | 2026-06-17 |  | 2026-06-17 | 2026-06-19 | 0
135 | IW13 | 2026-06-03 | 3 | Site Prep | Willett & Assoc. |  | Clearing | IW13¦Site Prep | IW13¦Clearing | 2 | 2026-06-22 |  | 2026-06-22 | 2026-06-23 | 0
136 | IW13 | 2026-06-03 | 4 | Footer | 3C Concrete | 3C Concrete | Site Prep | IW13¦Footer | IW13¦Site Prep | 4 | 2026-06-24 |  | 2026-06-24 | 2026-06-29 | 0
137 | IW13 | 2026-06-03 | 5 | Block | Julio H |  | Footer | IW13¦Block | IW13¦Footer | 10 | 2026-06-30 |  | 2026-06-30 | 2026-07-13 | 0
138 | IW13 | 2026-06-03 | 6 | French Drain | Jacob Hayden |  | Block | IW13¦French Drain | IW13¦Block | 2 | 2026-07-14 |  | 2026-07-14 | 2026-07-15 | 0
139 | IW13 | 2026-06-03 | 7 | Insulation Block | Tyler Champion |  | Block | IW13¦Insulation Block | IW13¦Block | 2 | 2026-07-14 |  | 2026-07-14 | 2026-07-15 | 0
140 | IW13 | 2026-06-03 | 8 | Rock Work |  |  | Insulation Block | IW13¦Rock Work | IW13¦Insulation Block | 2 | 2026-07-16 |  | 2026-07-16 | 2026-07-17 | 0
141 | IW13 | 2026-06-03 | 9 | HVAC Pre | Adco |  | Rock Work | IW13¦HVAC Pre | IW13¦Rock Work | 2 | 2026-07-20 |  | 2026-07-20 | 2026-07-21 | 0
142 | IW13 | 2026-06-03 | 10 | Plumbing Pre | Hays | Hays | Rock Work | IW13¦Plumbing Pre | IW13¦Rock Work | 5 | 2026-07-20 |  | 2026-07-20 | 2026-07-24 | 0
143 | IW13 | 2026-06-03 | 11 | Electrical Pre | Dave Kaler |  | Rock Work | IW13¦Electrical Pre | IW13¦Rock Work | 2 | 2026-07-20 |  | 2026-07-20 | 2026-07-21 | 0
144 | IW13 | 2026-06-03 | 12 | Slab | 3C Concrete | 3C Concrete | Plumbing Pre | IW13¦Slab | IW13¦Plumbing Pre | 4 | 2026-07-27 |  | 2026-07-27 | 2026-07-30 | 0
145 | IW13 | 2026-06-03 | 13 | Framing | Gerardo |  | Slab | IW13¦Framing | IW13¦Slab | 30 | 2026-07-31 |  | 2026-07-31 | 2026-09-10 | 0
146 | IW13 | 2026-06-03 | 14 | Roofing | Rod Smith |  | Framing | IW13¦Roofing | IW13¦Framing | 4 | 2026-09-11 |  | 2026-09-11 | 2026-09-16 | 0
147 | IW13 | 2026-06-03 | 15 | Brick | Julio H |  | Roofing | IW13¦Brick | IW13¦Roofing | 20 | 2026-09-17 |  | 2026-09-17 | 2026-10-14 | 0
148 | IW13 | 2026-06-03 | 16 | Stone | Julio H |  | Roofing | IW13¦Stone | IW13¦Roofing | 20 | 2026-09-17 |  | 2026-09-17 | 2026-10-14 | 0
149 | IW13 | 2026-06-03 | 17 | Siding | Gerardo |  | Roofing | IW13¦Siding | IW13¦Roofing | 20 | 2026-09-17 |  | 2026-09-17 | 2026-10-14 | 0
150 | IW13 | 2026-06-03 | 18 | Rough Grade |  |  | Brick | IW13¦Rough Grade | IW13¦Brick | 2 | 2026-10-15 |  | 2026-10-15 | 2026-10-16 | 0
151 | IW13 | 2026-06-03 | 19 | Irrigation | Ramiro |  | Rough Grade | IW13¦Irrigation | IW13¦Rough Grade | 2 | 2026-10-19 |  | 2026-10-19 | 2026-10-20 | 0
152 | IW13 | 2026-06-03 | 20 | Finish Grade | Jacob Hayden |  | Irrigation | IW13¦Finish Grade | IW13¦Irrigation | 2 | 2026-10-21 |  | 2026-10-21 | 2026-10-22 | 0
153 | IW13 | 2026-06-03 | 21 | Landscaping | Jacob Hayden |  | Irrigation | IW13¦Landscaping | IW13¦Irrigation | 2 | 2026-10-21 |  | 2026-10-21 | 2026-10-22 | 0
154 | IW13 | 2026-06-03 | 22 | Lawn Seeding | TruGreen |  | Finish Grade | IW13¦Lawn Seeding | IW13¦Finish Grade | 2 | 2026-10-23 |  | 2026-10-23 | 2026-10-26 | 0
155 | IW13 | 2026-06-03 | 23 | Gutter drains |  |  | Rough Grade | IW13¦Gutter drains | IW13¦Rough Grade | 2 | 2026-10-19 |  | 2026-10-19 | 2026-10-20 | 0
156 | IW13 | 2026-06-03 | 24 | HVAC Rough | Adco |  | Framing | IW13¦HVAC Rough | IW13¦Framing | 5 | 2026-09-11 |  | 2026-09-11 | 2026-09-17 | 0
157 | IW13 | 2026-06-03 | 25 | Plumbing Rough | Hays | Hays | Framing | IW13¦Plumbing Rough | IW13¦Framing | 5 | 2026-09-11 |  | 2026-09-11 | 2026-09-17 | 0
158 | IW13 | 2026-06-03 | 26 | Electrical Rough | Dave Kaler |  | Framing | IW13¦Electrical Rough | IW13¦Framing | 10 | 2026-09-11 |  | 2026-09-11 | 2026-09-24 | 0
159 | IW13 | 2026-06-03 | 27 | Insulation Walls | Tyler Champion |  | Electrical Rough | IW13¦Insulation Walls | IW13¦Electrical Rough | 2 | 2026-09-25 |  | 2026-09-25 | 2026-09-28 | 0
160 | IW13 | 2026-06-03 | 28 | Sheetrock | Bernall Constr. |  | Insulation Walls | IW13¦Sheetrock | IW13¦Insulation Walls | 15 | 2026-09-29 |  | 2026-09-29 | 2026-10-19 | 0
161 | IW13 | 2026-06-03 | 29 | Painting Primer | L&L Painting |  | Sheetrock | IW13¦Painting Primer | IW13¦Sheetrock | 3 | 2026-10-20 |  | 2026-10-20 | 2026-10-22 | 0
162 | IW13 | 2026-06-03 | 30 | Garage Doors | Danny Liedecher |  | Painting Primer | IW13¦Garage Doors | IW13¦Painting Primer | 2 | 2026-10-23 |  | 2026-10-23 | 2026-10-26 | 0
163 | IW13 | 2026-06-03 | 31 | Flooring | LW Contracting |  | Painting Primer | IW13¦Flooring | IW13¦Painting Primer | 5 | 2026-10-23 |  | 2026-10-23 | 2026-10-29 | 0
164 | IW13 | 2026-06-03 | 32 | Tile Work | LW Contracting |  | Painting Primer | IW13¦Tile Work | IW13¦Painting Primer | 8 | 2026-10-23 |  | 2026-10-23 | 2026-11-03 | 0
165 | IW13 | 2026-06-03 | 33 | Trim Interior | Matt Thorne | Matt Thorne | Flooring | IW13¦Trim Interior | IW13¦Flooring | 20 | 2026-10-30 |  | 2026-10-30 | 2026-11-26 | 0
166 | IW13 | 2026-06-03 | 34 | Trim Exterior | Matt Thorne | Matt Thorne | Siding | IW13¦Trim Exterior | IW13¦Siding | 2 | 2026-10-15 |  | 2026-10-15 | 2026-10-16 | 0
167 | IW13 | 2026-06-03 | 35 | Cabinets | Whittmer |  | Flooring | IW13¦Cabinets | IW13¦Flooring | 3 | 2026-10-30 |  | 2026-10-30 | 2026-11-03 | 0
168 | IW13 | 2026-06-03 | 36 | Countertops | Tate Granit |  | Cabinets | IW13¦Countertops | IW13¦Cabinets | 2 | 2026-11-04 |  | 2026-11-04 | 2026-11-05 | 0
169 | IW13 | 2026-06-03 | 37 | Painting Main | L&L Painting |  | Countertops | IW13¦Painting Main | IW13¦Countertops | 10 | 2026-11-06 |  | 2026-11-06 | 2026-11-19 | 0
170 | IW13 | 2026-06-03 | 38 | Appliances | Dave Kaler |  | Countertops | IW13¦Appliances | IW13¦Countertops | 2 | 2026-11-06 |  | 2026-11-06 | 2026-11-09 | 0
171 | IW13 | 2026-06-03 | 39 | HVAC Finish | Adco |  | Painting Main | IW13¦HVAC Finish | IW13¦Painting Main | 2 | 2026-11-20 |  | 2026-11-20 | 2026-11-23 | 0
172 | IW13 | 2026-06-03 | 40 | Plumbing Finish | Hays | Hays | Countertops | IW13¦Plumbing Finish | IW13¦Countertops | 2 | 2026-11-06 |  | 2026-11-06 | 2026-11-09 | 0
173 | IW13 | 2026-06-03 | 41 | Electrical Finish | Dave Kaler |  | Painting Main | IW13¦Electrical Finish | IW13¦Painting Main | 4 | 2026-11-20 |  | 2026-11-20 | 2026-11-25 | 0
174 | IW13 | 2026-06-03 | 42 | Insulation Ceiling | Tyler Champion |  | Electrical Finish | IW13¦Insulation Ceiling | IW13¦Electrical Finish | 2 | 2026-11-26 |  | 2026-11-26 | 2026-11-27 | 0
175 | IW13 | 2026-06-03 | 43 | Painting Finish | L&L Painting |  | Electrical Finish | IW13¦Painting Finish | IW13¦Electrical Finish | 5 | 2026-11-26 |  | 2026-11-26 | 2026-12-02 | 0
176 | IW13 | 2026-06-03 | 44 | Cleaning | Angies Cleaning |  | Painting Finish | IW13¦Cleaning | IW13¦Painting Finish | 3 | 2026-12-03 |  | 2026-12-03 | 2026-12-07 | 0
177 | IW14 | 2026-06-24 | 1 | Estimate | Willett & Assoc. |  |  | IW14¦Estimate |  | 10 | 2026-06-24 |  | 2026-06-24 | 2026-07-07 | 0
178 | IW14 | 2026-06-24 | 2 | Clearing | Willett & Assoc. |  | Estimate | IW14¦Clearing | IW14¦Estimate | 3 | 2026-07-08 |  | 2026-07-08 | 2026-07-10 | 0
179 | IW14 | 2026-06-24 | 3 | Site Prep | Willett & Assoc. |  | Clearing | IW14¦Site Prep | IW14¦Clearing | 2 | 2026-07-13 |  | 2026-07-13 | 2026-07-14 | 0
180 | IW14 | 2026-06-24 | 4 | Footer | 3C Concrete | 3C Concrete | Site Prep | IW14¦Footer | IW14¦Site Prep | 4 | 2026-07-15 |  | 2026-07-15 | 2026-07-20 | 0
181 | IW14 | 2026-06-24 | 5 | Block | Julio H |  | Footer | IW14¦Block | IW14¦Footer | 10 | 2026-07-21 |  | 2026-07-21 | 2026-08-03 | 0
182 | IW14 | 2026-06-24 | 6 | French Drain | Jacob Hayden |  | Block | IW14¦French Drain | IW14¦Block | 2 | 2026-08-04 |  | 2026-08-04 | 2026-08-05 | 0
183 | IW14 | 2026-06-24 | 7 | Insulation Block | Tyler Champion |  | Block | IW14¦Insulation Block | IW14¦Block | 2 | 2026-08-04 |  | 2026-08-04 | 2026-08-05 | 0
184 | IW14 | 2026-06-24 | 8 | Rock Work |  |  | Insulation Block | IW14¦Rock Work | IW14¦Insulation Block | 2 | 2026-08-06 |  | 2026-08-06 | 2026-08-07 | 0
185 | IW14 | 2026-06-24 | 9 | HVAC Pre | Adco |  | Rock Work | IW14¦HVAC Pre | IW14¦Rock Work | 2 | 2026-08-10 |  | 2026-08-10 | 2026-08-11 | 0
186 | IW14 | 2026-06-24 | 10 | Plumbing Pre | Hays | Hays | Rock Work | IW14¦Plumbing Pre | IW14¦Rock Work | 5 | 2026-08-10 |  | 2026-08-10 | 2026-08-14 | 0
187 | IW14 | 2026-06-24 | 11 | Electrical Pre | Dave Kaler |  | Rock Work | IW14¦Electrical Pre | IW14¦Rock Work | 2 | 2026-08-10 |  | 2026-08-10 | 2026-08-11 | 0
188 | IW14 | 2026-06-24 | 12 | Slab | 3C Concrete | 3C Concrete | Plumbing Pre | IW14¦Slab | IW14¦Plumbing Pre | 4 | 2026-08-17 |  | 2026-08-17 | 2026-08-20 | 0
189 | IW14 | 2026-06-24 | 13 | Framing | Gerardo |  | Slab | IW14¦Framing | IW14¦Slab | 30 | 2026-08-21 |  | 2026-08-21 | 2026-10-01 | 0
190 | IW14 | 2026-06-24 | 14 | Roofing | Rod Smith |  | Framing | IW14¦Roofing | IW14¦Framing | 4 | 2026-10-02 |  | 2026-10-02 | 2026-10-07 | 0
191 | IW14 | 2026-06-24 | 15 | Brick | Julio H |  | Roofing | IW14¦Brick | IW14¦Roofing | 20 | 2026-10-08 |  | 2026-10-08 | 2026-11-04 | 0
192 | IW14 | 2026-06-24 | 16 | Stone | Julio H |  | Roofing | IW14¦Stone | IW14¦Roofing | 20 | 2026-10-08 |  | 2026-10-08 | 2026-11-04 | 0
193 | IW14 | 2026-06-24 | 17 | Siding | Gerardo |  | Roofing | IW14¦Siding | IW14¦Roofing | 20 | 2026-10-08 |  | 2026-10-08 | 2026-11-04 | 0
194 | IW14 | 2026-06-24 | 18 | Rough Grade |  |  | Brick | IW14¦Rough Grade | IW14¦Brick | 2 | 2026-11-05 |  | 2026-11-05 | 2026-11-06 | 0
195 | IW14 | 2026-06-24 | 19 | Irrigation | Ramiro |  | Rough Grade | IW14¦Irrigation | IW14¦Rough Grade | 2 | 2026-11-09 |  | 2026-11-09 | 2026-11-10 | 0
196 | IW14 | 2026-06-24 | 20 | Finish Grade | Jacob Hayden |  | Irrigation | IW14¦Finish Grade | IW14¦Irrigation | 2 | 2026-11-11 |  | 2026-11-11 | 2026-11-12 | 0
197 | IW14 | 2026-06-24 | 21 | Landscaping | Jacob Hayden |  | Irrigation | IW14¦Landscaping | IW14¦Irrigation | 2 | 2026-11-11 |  | 2026-11-11 | 2026-11-12 | 0
198 | IW14 | 2026-06-24 | 22 | Lawn Seeding | TruGreen |  | Finish Grade | IW14¦Lawn Seeding | IW14¦Finish Grade | 2 | 2026-11-13 |  | 2026-11-13 | 2026-11-16 | 0
199 | IW14 | 2026-06-24 | 23 | Gutter drains |  |  | Rough Grade | IW14¦Gutter drains | IW14¦Rough Grade | 2 | 2026-11-09 |  | 2026-11-09 | 2026-11-10 | 0
200 | IW14 | 2026-06-24 | 24 | HVAC Rough | Adco |  | Framing | IW14¦HVAC Rough | IW14¦Framing | 5 | 2026-10-02 |  | 2026-10-02 | 2026-10-08 | 0
201 | IW14 | 2026-06-24 | 25 | Plumbing Rough | Hays | Hays | Framing | IW14¦Plumbing Rough | IW14¦Framing | 5 | 2026-10-02 |  | 2026-10-02 | 2026-10-08 | 0
202 | IW14 | 2026-06-24 | 26 | Electrical Rough | Dave Kaler |  | Framing | IW14¦Electrical Rough | IW14¦Framing | 10 | 2026-10-02 |  | 2026-10-02 | 2026-10-15 | 0
203 | IW14 | 2026-06-24 | 27 | Insulation Walls | Tyler Champion |  | Electrical Rough | IW14¦Insulation Walls | IW14¦Electrical Rough | 2 | 2026-10-16 |  | 2026-10-16 | 2026-10-19 | 0
204 | IW14 | 2026-06-24 | 28 | Sheetrock | Bernall Constr. |  | Insulation Walls | IW14¦Sheetrock | IW14¦Insulation Walls | 15 | 2026-10-20 |  | 2026-10-20 | 2026-11-09 | 0
205 | IW14 | 2026-06-24 | 29 | Painting Primer | L&L Painting |  | Sheetrock | IW14¦Painting Primer | IW14¦Sheetrock | 3 | 2026-11-10 |  | 2026-11-10 | 2026-11-12 | 0
206 | IW14 | 2026-06-24 | 30 | Garage Doors | Danny Liedecher |  | Painting Primer | IW14¦Garage Doors | IW14¦Painting Primer | 2 | 2026-11-13 |  | 2026-11-13 | 2026-11-16 | 0
207 | IW14 | 2026-06-24 | 31 | Flooring | LW Contracting |  | Painting Primer | IW14¦Flooring | IW14¦Painting Primer | 5 | 2026-11-13 |  | 2026-11-13 | 2026-11-19 | 0
208 | IW14 | 2026-06-24 | 32 | Tile Work | LW Contracting |  | Painting Primer | IW14¦Tile Work | IW14¦Painting Primer | 8 | 2026-11-13 |  | 2026-11-13 | 2026-11-24 | 0
209 | IW14 | 2026-06-24 | 33 | Trim Interior | Matt Thorne | Matt Thorne | Flooring | IW14¦Trim Interior | IW14¦Flooring | 20 | 2026-11-20 |  | 2026-11-20 | 2026-12-17 | 0
210 | IW14 | 2026-06-24 | 34 | Trim Exterior | Matt Thorne | Matt Thorne | Siding | IW14¦Trim Exterior | IW14¦Siding | 2 | 2026-11-05 |  | 2026-11-05 | 2026-11-06 | 0
211 | IW14 | 2026-06-24 | 35 | Cabinets | Whittmer |  | Flooring | IW14¦Cabinets | IW14¦Flooring | 3 | 2026-11-20 |  | 2026-11-20 | 2026-11-24 | 0
212 | IW14 | 2026-06-24 | 36 | Countertops | Tate Granit |  | Cabinets | IW14¦Countertops | IW14¦Cabinets | 2 | 2026-11-25 |  | 2026-11-25 | 2026-11-26 | 0
213 | IW14 | 2026-06-24 | 37 | Painting Main | L&L Painting |  | Countertops | IW14¦Painting Main | IW14¦Countertops | 10 | 2026-11-27 |  | 2026-11-27 | 2026-12-10 | 0
214 | IW14 | 2026-06-24 | 38 | Appliances | Dave Kaler |  | Countertops | IW14¦Appliances | IW14¦Countertops | 2 | 2026-11-27 |  | 2026-11-27 | 2026-11-30 | 0
215 | IW14 | 2026-06-24 | 39 | HVAC Finish | Adco |  | Painting Main | IW14¦HVAC Finish | IW14¦Painting Main | 2 | 2026-12-11 |  | 2026-12-11 | 2026-12-14 | 0
216 | IW14 | 2026-06-24 | 40 | Plumbing Finish | Hays | Hays | Countertops | IW14¦Plumbing Finish | IW14¦Countertops | 2 | 2026-11-27 |  | 2026-11-27 | 2026-11-30 | 0
217 | IW14 | 2026-06-24 | 41 | Electrical Finish | Dave Kaler |  | Painting Main | IW14¦Electrical Finish | IW14¦Painting Main | 4 | 2026-12-11 |  | 2026-12-11 | 2026-12-16 | 0
218 | IW14 | 2026-06-24 | 42 | Insulation Ceiling | Tyler Champion |  | Electrical Finish | IW14¦Insulation Ceiling | IW14¦Electrical Finish | 2 | 2026-12-17 |  | 2026-12-17 | 2026-12-18 | 0
219 | IW14 | 2026-06-24 | 43 | Painting Finish | L&L Painting |  | Electrical Finish | IW14¦Painting Finish | IW14¦Electrical Finish | 5 | 2026-12-17 |  | 2026-12-17 | 2026-12-23 | 0
220 | IW14 | 2026-06-24 | 44 | Cleaning | Angies Cleaning |  | Painting Finish | IW14¦Cleaning | IW14¦Painting Finish | 3 | 2026-12-24 |  | 2026-12-24 | 2026-12-28 | 0
221 | IW15 | 2026-07-15 | 1 | Estimate | Willett & Assoc. |  |  | IW15¦Estimate |  | 10 | 2026-07-15 |  | 2026-07-15 | 2026-07-28 | 0
222 | IW15 | 2026-07-15 | 2 | Clearing | Willett & Assoc. |  | Estimate | IW15¦Clearing | IW15¦Estimate | 3 | 2026-07-29 |  | 2026-07-29 | 2026-07-31 | 0
223 | IW15 | 2026-07-15 | 3 | Site Prep | Willett & Assoc. |  | Clearing | IW15¦Site Prep | IW15¦Clearing | 2 | 2026-08-03 |  | 2026-08-03 | 2026-08-04 | 0
224 | IW15 | 2026-07-15 | 4 | Footer | 3C Concrete | 3C Concrete | Site Prep | IW15¦Footer | IW15¦Site Prep | 4 | 2026-08-05 |  | 2026-08-05 | 2026-08-10 | 0
225 | IW15 | 2026-07-15 | 5 | Block | Julio H |  | Footer | IW15¦Block | IW15¦Footer | 10 | 2026-08-11 |  | 2026-08-11 | 2026-08-24 | 0
226 | IW15 | 2026-07-15 | 6 | French Drain | Jacob Hayden |  | Block | IW15¦French Drain | IW15¦Block | 2 | 2026-08-25 |  | 2026-08-25 | 2026-08-26 | 0
227 | IW15 | 2026-07-15 | 7 | Insulation Block | Tyler Champion |  | Block | IW15¦Insulation Block | IW15¦Block | 2 | 2026-08-25 |  | 2026-08-25 | 2026-08-26 | 0
228 | IW15 | 2026-07-15 | 8 | Rock Work |  |  | Insulation Block | IW15¦Rock Work | IW15¦Insulation Block | 2 | 2026-08-27 |  | 2026-08-27 | 2026-08-28 | 0
229 | IW15 | 2026-07-15 | 9 | HVAC Pre | Adco |  | Rock Work | IW15¦HVAC Pre | IW15¦Rock Work | 2 | 2026-08-31 |  | 2026-08-31 | 2026-09-01 | 0
230 | IW15 | 2026-07-15 | 10 | Plumbing Pre | Hays | Hays | Rock Work | IW15¦Plumbing Pre | IW15¦Rock Work | 5 | 2026-08-31 |  | 2026-08-31 | 2026-09-04 | 0
231 | IW15 | 2026-07-15 | 11 | Electrical Pre | Dave Kaler |  | Rock Work | IW15¦Electrical Pre | IW15¦Rock Work | 2 | 2026-08-31 |  | 2026-08-31 | 2026-09-01 | 0
232 | IW15 | 2026-07-15 | 12 | Slab | 3C Concrete | 3C Concrete | Plumbing Pre | IW15¦Slab | IW15¦Plumbing Pre | 4 | 2026-09-07 |  | 2026-09-07 | 2026-09-10 | 0
233 | IW15 | 2026-07-15 | 13 | Framing | Gerardo |  | Slab | IW15¦Framing | IW15¦Slab | 30 | 2026-09-11 |  | 2026-09-11 | 2026-10-22 | 0
234 | IW15 | 2026-07-15 | 14 | Roofing | Rod Smith |  | Framing | IW15¦Roofing | IW15¦Framing | 4 | 2026-10-23 |  | 2026-10-23 | 2026-10-28 | 0
235 | IW15 | 2026-07-15 | 15 | Brick | Julio H |  | Roofing | IW15¦Brick | IW15¦Roofing | 20 | 2026-10-29 |  | 2026-10-29 | 2026-11-25 | 0
236 | IW15 | 2026-07-15 | 16 | Stone | Julio H |  | Roofing | IW15¦Stone | IW15¦Roofing | 20 | 2026-10-29 |  | 2026-10-29 | 2026-11-25 | 0
237 | IW15 | 2026-07-15 | 17 | Siding | Gerardo |  | Roofing | IW15¦Siding | IW15¦Roofing | 20 | 2026-10-29 |  | 2026-10-29 | 2026-11-25 | 0
238 | IW15 | 2026-07-15 | 18 | Rough Grade |  |  | Brick | IW15¦Rough Grade | IW15¦Brick | 2 | 2026-11-26 |  | 2026-11-26 | 2026-11-27 | 0
239 | IW15 | 2026-07-15 | 19 | Irrigation | Ramiro |  | Rough Grade | IW15¦Irrigation | IW15¦Rough Grade | 2 | 2026-11-30 |  | 2026-11-30 | 2026-12-01 | 0
240 | IW15 | 2026-07-15 | 20 | Finish Grade | Jacob Hayden |  | Irrigation | IW15¦Finish Grade | IW15¦Irrigation | 2 | 2026-12-02 |  | 2026-12-02 | 2026-12-03 | 0
241 | IW15 | 2026-07-15 | 21 | Landscaping | Jacob Hayden |  | Irrigation | IW15¦Landscaping | IW15¦Irrigation | 2 | 2026-12-02 |  | 2026-12-02 | 2026-12-03 | 0
242 | IW15 | 2026-07-15 | 22 | Lawn Seeding | TruGreen |  | Finish Grade | IW15¦Lawn Seeding | IW15¦Finish Grade | 2 | 2026-12-04 |  | 2026-12-04 | 2026-12-07 | 0
243 | IW15 | 2026-07-15 | 23 | Gutter drains |  |  | Rough Grade | IW15¦Gutter drains | IW15¦Rough Grade | 2 | 2026-11-30 |  | 2026-11-30 | 2026-12-01 | 0
244 | IW15 | 2026-07-15 | 24 | HVAC Rough | Adco |  | Framing | IW15¦HVAC Rough | IW15¦Framing | 5 | 2026-10-23 |  | 2026-10-23 | 2026-10-29 | 0
245 | IW15 | 2026-07-15 | 25 | Plumbing Rough | Hays | Hays | Framing | IW15¦Plumbing Rough | IW15¦Framing | 5 | 2026-10-23 |  | 2026-10-23 | 2026-10-29 | 0
246 | IW15 | 2026-07-15 | 26 | Electrical Rough | Dave Kaler |  | Framing | IW15¦Electrical Rough | IW15¦Framing | 10 | 2026-10-23 |  | 2026-10-23 | 2026-11-05 | 0
247 | IW15 | 2026-07-15 | 27 | Insulation Walls | Tyler Champion |  | Electrical Rough | IW15¦Insulation Walls | IW15¦Electrical Rough | 2 | 2026-11-06 |  | 2026-11-06 | 2026-11-09 | 0
248 | IW15 | 2026-07-15 | 28 | Sheetrock | Bernall Constr. |  | Insulation Walls | IW15¦Sheetrock | IW15¦Insulation Walls | 15 | 2026-11-10 |  | 2026-11-10 | 2026-11-30 | 0
249 | IW15 | 2026-07-15 | 29 | Painting Primer | L&L Painting |  | Sheetrock | IW15¦Painting Primer | IW15¦Sheetrock | 3 | 2026-12-01 |  | 2026-12-01 | 2026-12-03 | 0
250 | IW15 | 2026-07-15 | 30 | Garage Doors | Danny Liedecher |  | Painting Primer | IW15¦Garage Doors | IW15¦Painting Primer | 2 | 2026-12-04 |  | 2026-12-04 | 2026-12-07 | 0
251 | IW15 | 2026-07-15 | 31 | Flooring | LW Contracting |  | Painting Primer | IW15¦Flooring | IW15¦Painting Primer | 5 | 2026-12-04 |  | 2026-12-04 | 2026-12-10 | 0
252 | IW15 | 2026-07-15 | 32 | Tile Work | LW Contracting |  | Painting Primer | IW15¦Tile Work | IW15¦Painting Primer | 8 | 2026-12-04 |  | 2026-12-04 | 2026-12-15 | 0
253 | IW15 | 2026-07-15 | 33 | Trim Interior | Matt Thorne | Matt Thorne | Flooring | IW15¦Trim Interior | IW15¦Flooring | 20 | 2026-12-11 |  | 2026-12-11 | 2027-01-07 | 0
254 | IW15 | 2026-07-15 | 34 | Trim Exterior | Matt Thorne | Matt Thorne | Siding | IW15¦Trim Exterior | IW15¦Siding | 2 | 2026-11-26 |  | 2026-11-26 | 2026-11-27 | 0
255 | IW15 | 2026-07-15 | 35 | Cabinets | Whittmer |  | Flooring | IW15¦Cabinets | IW15¦Flooring | 3 | 2026-12-11 |  | 2026-12-11 | 2026-12-15 | 0
256 | IW15 | 2026-07-15 | 36 | Countertops | Tate Granit |  | Cabinets | IW15¦Countertops | IW15¦Cabinets | 2 | 2026-12-16 |  | 2026-12-16 | 2026-12-17 | 0
257 | IW15 | 2026-07-15 | 37 | Painting Main | L&L Painting |  | Countertops | IW15¦Painting Main | IW15¦Countertops | 10 | 2026-12-18 |  | 2026-12-18 | 2026-12-31 | 0
258 | IW15 | 2026-07-15 | 38 | Appliances | Dave Kaler |  | Countertops | IW15¦Appliances | IW15¦Countertops | 2 | 2026-12-18 |  | 2026-12-18 | 2026-12-21 | 0
259 | IW15 | 2026-07-15 | 39 | HVAC Finish | Adco |  | Painting Main | IW15¦HVAC Finish | IW15¦Painting Main | 2 | 2027-01-01 |  | 2027-01-01 | 2027-01-04 | 0
260 | IW15 | 2026-07-15 | 40 | Plumbing Finish | Hays | Hays | Countertops | IW15¦Plumbing Finish | IW15¦Countertops | 2 | 2026-12-18 |  | 2026-12-18 | 2026-12-21 | 0
261 | IW15 | 2026-07-15 | 41 | Electrical Finish | Dave Kaler |  | Painting Main | IW15¦Electrical Finish | IW15¦Painting Main | 4 | 2027-01-01 |  | 2027-01-01 | 2027-01-06 | 0
262 | IW15 | 2026-07-15 | 42 | Insulation Ceiling | Tyler Champion |  | Electrical Finish | IW15¦Insulation Ceiling | IW15¦Electrical Finish | 2 | 2027-01-07 |  | 2027-01-07 | 2027-01-08 | 0
263 | IW15 | 2026-07-15 | 43 | Painting Finish | L&L Painting |  | Electrical Finish | IW15¦Painting Finish | IW15¦Electrical Finish | 5 | 2027-01-07 |  | 2027-01-07 | 2027-01-13 | 0
264 | IW15 | 2026-07-15 | 44 | Cleaning | Angies Cleaning |  | Painting Finish | IW15¦Cleaning | IW15¦Painting Finish | 3 | 2027-01-14 |  | 2027-01-14 | 2027-01-18 | 0
Formulas:
Project Start = INDEX(Projects!$B2:B100,MATCH([Project],Projects!$A2:A100,0))
Logic Start = IF([Dependency]="",[Project Start],WORKDAY(INDEX(O2:O2000,MATCH([Dependency Key],I2:I2000,0)),1))
Calculated Start = IF([Bottleneck Vendor]="",[Logic Start],MAX([Logic Start],IF([Prev Bottleneck Finish]="",[Logic Start],WORKDAY([Prev Bottleneck Finish],1))))
Calculated Finish = WORKDAY([Calculated Start],[Days]-1)
Delay Days = MAX(0,NETWORKDAYS([Logic Start],[Calculated Start])-1)

## Engine Gantt
Project | Scope | Subcontractor | Bottleneck Vendor | Start | Finish | Days | Delay | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06
[8 empty] | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
IW10 | Estimate | Willett & Assoc. | 0 | 2026-04-01 | 2026-04-14 | 10 | 0
IW10 | Clearing | Willett & Assoc. | 0 | 2026-04-15 | 2026-04-17 | 3 | 0
IW10 | Site Prep | Willett & Assoc. | 0 | 2026-04-20 | 2026-04-21 | 2 | 0
IW10 | Footer | 3C Concrete | 3C Concrete | 2026-04-22 | 2026-04-27 | 4 | 0
IW10 | Block | Julio H | 0 | 2026-04-28 | 2026-05-11 | 10 | 0
IW10 | French Drain | Jacob Hayden | 0 | 2026-05-12 | 2026-05-13 | 2 | 0
IW10 | Insulation Block | Tyler Champion | 0 | 2026-05-12 | 2026-05-13 | 2 | 0
IW10 | Rock Work | 0 | 0 | 2026-05-14 | 2026-05-15 | 2 | 0
IW10 | HVAC Pre | Adco | 0 | 2026-05-18 | 2026-05-19 | 2 | 0
IW10 | Plumbing Pre | Hays | Hays | 2026-05-18 | 2026-05-22 | 5 | 0
IW10 | Electrical Pre | Dave Kaler | 0 | 2026-05-18 | 2026-05-19 | 2 | 0
IW10 | Slab | 3C Concrete | 3C Concrete | 2026-05-25 | 2026-05-28 | 4 | 0
IW10 | Framing | Gerardo | 0 | 2026-05-29 | 2026-07-09 | 30 | 0
IW10 | Roofing | Rod Smith | 0 | 2026-07-10 | 2026-07-15 | 4 | 0
IW10 | Brick | Julio H | 0 | 2026-07-16 | 2026-08-12 | 20 | 0
IW10 | Stone | Julio H | 0 | 2026-07-16 | 2026-08-12 | 20 | 0
IW10 | Siding | Gerardo | 0 | 2026-07-16 | 2026-08-12 | 20 | 0
IW10 | Rough Grade | 0 | 0 | 2026-08-13 | 2026-08-14 | 2 | 0
IW10 | Irrigation | Ramiro | 0 | 2026-08-17 | 2026-08-18 | 2 | 0
IW10 | Finish Grade | Jacob Hayden | 0 | 2026-08-19 | 2026-08-20 | 2 | 0
IW10 | Landscaping | Jacob Hayden | 0 | 2026-08-19 | 2026-08-20 | 2 | 0
IW10 | Lawn Seeding | TruGreen | 0 | 2026-08-21 | 2026-08-24 | 2 | 0
IW10 | Gutter drains | 0 | 0 | 2026-08-17 | 2026-08-18 | 2 | 0
IW10 | HVAC Rough | Adco | 0 | 2026-07-10 | 2026-07-16 | 5 | 0
IW10 | Plumbing Rough | Hays | Hays | 2026-07-10 | 2026-07-16 | 5 | 0
IW10 | Electrical Rough | Dave Kaler | 0 | 2026-07-10 | 2026-07-23 | 10 | 0
IW10 | Insulation Walls | Tyler Champion | 0 | 2026-07-24 | 2026-07-27 | 2 | 0
IW10 | Sheetrock | Bernall Constr. | 0 | 2026-07-28 | 2026-08-17 | 15 | 0
IW10 | Painting Primer | L&L Painting | 0 | 2026-08-18 | 2026-08-20 | 3 | 0
IW10 | Garage Doors | Danny Liedecher | 0 | 2026-08-21 | 2026-08-24 | 2 | 0
IW10 | Flooring | LW Contracting | 0 | 2026-08-21 | 2026-08-27 | 5 | 0
IW10 | Tile Work | LW Contracting | 0 | 2026-08-21 | 2026-09-01 | 8 | 0
IW10 | Trim Interior | Matt Thorne | Matt Thorne | 2026-08-28 | 2026-09-24 | 20 | 0
IW10 | Trim Exterior | Matt Thorne | Matt Thorne | 2026-08-13 | 2026-08-14 | 2 | 0
IW10 | Cabinets | Whittmer | 0 | 2026-08-28 | 2026-09-01 | 3 | 0
IW10 | Countertops | Tate Granit | 0 | 2026-09-02 | 2026-09-03 | 2 | 0
IW10 | Painting Main | L&L Painting | 0 | 2026-09-04 | 2026-09-17 | 10 | 0
IW10 | Appliances | Dave Kaler | 0 | 2026-09-04 | 2026-09-07 | 2 | 0
IW10 | HVAC Finish | Adco | 0 | 2026-09-18 | 2026-09-21 | 2 | 0
IW10 | Plumbing Finish | Hays | Hays | 2026-09-04 | 2026-09-07 | 2 | 0
IW10 | Electrical Finish | Dave Kaler | 0 | 2026-09-18 | 2026-09-23 | 4 | 0
IW10 | Insulation Ceiling | Tyler Champion | 0 | 2026-09-24 | 2026-09-25 | 2 | 0
IW10 | Painting Finish | L&L Painting | 0 | 2026-09-24 | 2026-09-30 | 5 | 0
IW10 | Cleaning | Angies Cleaning | 0 | 2026-10-01 | 2026-10-05 | 3 | 0
IW11 | Estimate | Willett & Assoc. | 0 | 2026-04-22 | 2026-05-05 | 10 | 0
IW11 | Clearing | Willett & Assoc. | 0 | 2026-05-06 | 2026-05-08 | 3 | 0
IW11 | Site Prep | Willett & Assoc. | 0 | 2026-05-11 | 2026-05-12 | 2 | 0
IW11 | Footer | 3C Concrete | 3C Concrete | 2026-05-13 | 2026-05-18 | 4 | 0
IW11 | Block | Julio H | 0 | 2026-05-19 | 2026-06-01 | 10 | 0
IW11 | French Drain | Jacob Hayden | 0 | 2026-06-02 | 2026-06-03 | 2 | 0
IW11 | Insulation Block | Tyler Champion | 0 | 2026-06-02 | 2026-06-03 | 2 | 0
IW11 | Rock Work | 0 | 0 | 2026-06-04 | 2026-06-05 | 2 | 0
IW11 | HVAC Pre | Adco | 0 | 2026-06-08 | 2026-06-09 | 2 | 0
IW11 | Plumbing Pre | Hays | Hays | 2026-06-08 | 2026-06-12 | 5 | 0
IW11 | Electrical Pre | Dave Kaler | 0 | 2026-06-08 | 2026-06-09 | 2 | 0
IW11 | Slab | 3C Concrete | 3C Concrete | 2026-06-15 | 2026-06-18 | 4 | 0
IW11 | Framing | Gerardo | 0 | 2026-06-19 | 2026-07-30 | 30 | 0
IW11 | Roofing | Rod Smith | 0 | 2026-07-31 | 2026-08-05 | 4 | 0
IW11 | Brick | Julio H | 0 | 2026-08-06 | 2026-09-02 | 20 | 0
IW11 | Stone | Julio H | 0 | 2026-08-06 | 2026-09-02 | 20 | 0
IW11 | Siding | Gerardo | 0 | 2026-08-06 | 2026-09-02 | 20 | 0
IW11 | Rough Grade | 0 | 0 | 2026-09-03 | 2026-09-04 | 2 | 0
IW11 | Irrigation | Ramiro | 0 | 2026-09-07 | 2026-09-08 | 2 | 0
IW11 | Finish Grade | Jacob Hayden | 0 | 2026-09-09 | 2026-09-10 | 2 | 0
IW11 | Landscaping | Jacob Hayden | 0 | 2026-09-09 | 2026-09-10 | 2 | 0
IW11 | Lawn Seeding | TruGreen | 0 | 2026-09-11 | 2026-09-14 | 2 | 0
IW11 | Gutter drains | 0 | 0 | 2026-09-07 | 2026-09-08 | 2 | 0
IW11 | HVAC Rough | Adco | 0 | 2026-07-31 | 2026-08-06 | 5 | 0
IW11 | Plumbing Rough | Hays | Hays | 2026-07-31 | 2026-08-06 | 5 | 0
IW11 | Electrical Rough | Dave Kaler | 0 | 2026-07-31 | 2026-08-13 | 10 | 0
IW11 | Insulation Walls | Tyler Champion | 0 | 2026-08-14 | 2026-08-17 | 2 | 0
IW11 | Sheetrock | Bernall Constr. | 0 | 2026-08-18 | 2026-09-07 | 15 | 0
IW11 | Painting Primer | L&L Painting | 0 | 2026-09-08 | 2026-09-10 | 3 | 0
IW11 | Garage Doors | Danny Liedecher | 0 | 2026-09-11 | 2026-09-14 | 2 | 0
IW11 | Flooring | LW Contracting | 0 | 2026-09-11 | 2026-09-17 | 5 | 0
IW11 | Tile Work | LW Contracting | 0 | 2026-09-11 | 2026-09-22 | 8 | 0
IW11 | Trim Interior | Matt Thorne | Matt Thorne | 2026-09-18 | 2026-10-15 | 20 | 0
IW11 | Trim Exterior | Matt Thorne | Matt Thorne | 2026-09-03 | 2026-09-04 | 2 | 0
IW11 | Cabinets | Whittmer | 0 | 2026-09-18 | 2026-09-22 | 3 | 0
IW11 | Countertops | Tate Granit | 0 | 2026-09-23 | 2026-09-24 | 2 | 0
IW11 | Painting Main | L&L Painting | 0 | 2026-09-25 | 2026-10-08 | 10 | 0
IW11 | Appliances | Dave Kaler | 0 | 2026-09-25 | 2026-09-28 | 2 | 0
IW11 | HVAC Finish | Adco | 0 | 2026-10-09 | 2026-10-12 | 2 | 0
IW11 | Plumbing Finish | Hays | Hays | 2026-09-25 | 2026-09-28 | 2 | 0
IW11 | Electrical Finish | Dave Kaler | 0 | 2026-10-09 | 2026-10-14 | 4 | 0
IW11 | Insulation Ceiling | Tyler Champion | 0 | 2026-10-15 | 2026-10-16 | 2 | 0
IW11 | Painting Finish | L&L Painting | 0 | 2026-10-15 | 2026-10-21 | 5 | 0
IW11 | Cleaning | Angies Cleaning | 0 | 2026-10-22 | 2026-10-26 | 3 | 0
IW12 | Estimate | Willett & Assoc. | 0 | 2026-05-13 | 2026-05-26 | 10 | 0
IW12 | Clearing | Willett & Assoc. | 0 | 2026-05-27 | 2026-05-29 | 3 | 0
IW12 | Site Prep | Willett & Assoc. | 0 | 2026-06-01 | 2026-06-02 | 2 | 0
IW12 | Footer | 3C Concrete | 3C Concrete | 2026-06-03 | 2026-06-08 | 4 | 0
IW12 | Block | Julio H | 0 | 2026-06-09 | 2026-06-22 | 10 | 0
IW12 | French Drain | Jacob Hayden | 0 | 2026-06-23 | 2026-06-24 | 2 | 0
IW12 | Insulation Block | Tyler Champion | 0 | 2026-06-23 | 2026-06-24 | 2 | 0
IW12 | Rock Work | 0 | 0 | 2026-06-25 | 2026-06-26 | 2 | 0
IW12 | HVAC Pre | Adco | 0 | 2026-06-29 | 2026-06-30 | 2 | 0
IW12 | Plumbing Pre | Hays | Hays | 2026-06-29 | 2026-07-03 | 5 | 0
IW12 | Electrical Pre | Dave Kaler | 0 | 2026-06-29 | 2026-06-30 | 2 | 0
IW12 | Slab | 3C Concrete | 3C Concrete | 2026-07-06 | 2026-07-09 | 4 | 0
IW12 | Framing | Gerardo | 0 | 2026-07-10 | 2026-08-20 | 30 | 0
IW12 | Roofing | Rod Smith | 0 | 2026-08-21 | 2026-08-26 | 4 | 0
IW12 | Brick | Julio H | 0 | 2026-08-27 | 2026-09-23 | 20 | 0
IW12 | Stone | Julio H | 0 | 2026-08-27 | 2026-09-23 | 20 | 0
IW12 | Siding | Gerardo | 0 | 2026-08-27 | 2026-09-23 | 20 | 0
IW12 | Rough Grade | 0 | 0 | 2026-09-24 | 2026-09-25 | 2 | 0
IW12 | Irrigation | Ramiro | 0 | 2026-09-28 | 2026-09-29 | 2 | 0
IW12 | Finish Grade | Jacob Hayden | 0 | 2026-09-30 | 2026-10-01 | 2 | 0
IW12 | Landscaping | Jacob Hayden | 0 | 2026-09-30 | 2026-10-01 | 2 | 0
IW12 | Lawn Seeding | TruGreen | 0 | 2026-10-02 | 2026-10-05 | 2 | 0
IW12 | Gutter drains | 0 | 0 | 2026-09-28 | 2026-09-29 | 2 | 0
IW12 | HVAC Rough | Adco | 0 | 2026-08-21 | 2026-08-27 | 5 | 0
IW12 | Plumbing Rough | Hays | Hays | 2026-08-21 | 2026-08-27 | 5 | 0
IW12 | Electrical Rough | Dave Kaler | 0 | 2026-08-21 | 2026-09-03 | 10 | 0
IW12 | Insulation Walls | Tyler Champion | 0 | 2026-09-04 | 2026-09-07 | 2 | 0
IW12 | Sheetrock | Bernall Constr. | 0 | 2026-09-08 | 2026-09-28 | 15 | 0
IW12 | Painting Primer | L&L Painting | 0 | 2026-09-29 | 2026-10-01 | 3 | 0
IW12 | Garage Doors | Danny Liedecher | 0 | 2026-10-02 | 2026-10-05 | 2 | 0
IW12 | Flooring | LW Contracting | 0 | 2026-10-02 | 2026-10-08 | 5 | 0
IW12 | Tile Work | LW Contracting | 0 | 2026-10-02 | 2026-10-13 | 8 | 0
IW12 | Trim Interior | Matt Thorne | Matt Thorne | 2026-10-09 | 2026-11-05 | 20 | 0
IW12 | Trim Exterior | Matt Thorne | Matt Thorne | 2026-09-24 | 2026-09-25 | 2 | 0
IW12 | Cabinets | Whittmer | 0 | 2026-10-09 | 2026-10-13 | 3 | 0
IW12 | Countertops | Tate Granit | 0 | 2026-10-14 | 2026-10-15 | 2 | 0
IW12 | Painting Main | L&L Painting | 0 | 2026-10-16 | 2026-10-29 | 10 | 0
IW12 | Appliances | Dave Kaler | 0 | 2026-10-16 | 2026-10-19 | 2 | 0
IW12 | HVAC Finish | Adco | 0 | 2026-10-30 | 2026-11-02 | 2 | 0
IW12 | Plumbing Finish | Hays | Hays | 2026-10-16 | 2026-10-19 | 2 | 0
IW12 | Electrical Finish | Dave Kaler | 0 | 2026-10-30 | 2026-11-04 | 4 | 0
IW12 | Insulation Ceiling | Tyler Champion | 0 | 2026-11-05 | 2026-11-06 | 2 | 0
IW12 | Painting Finish | L&L Painting | 0 | 2026-11-05 | 2026-11-11 | 5 | 0
IW12 | Cleaning | Angies Cleaning | 0 | 2026-11-12 | 2026-11-16 | 3 | 0
IW13 | Estimate | Willett & Assoc. | 0 | 2026-06-03 | 2026-06-16 | 10 | 0
IW13 | Clearing | Willett & Assoc. | 0 | 2026-06-17 | 2026-06-19 | 3 | 0
IW13 | Site Prep | Willett & Assoc. | 0 | 2026-06-22 | 2026-06-23 | 2 | 0
IW13 | Footer | 3C Concrete | 3C Concrete | 2026-06-24 | 2026-06-29 | 4 | 0
IW13 | Block | Julio H | 0 | 2026-06-30 | 2026-07-13 | 10 | 0
IW13 | French Drain | Jacob Hayden | 0 | 2026-07-14 | 2026-07-15 | 2 | 0
IW13 | Insulation Block | Tyler Champion | 0 | 2026-07-14 | 2026-07-15 | 2 | 0
IW13 | Rock Work | 0 | 0 | 2026-07-16 | 2026-07-17 | 2 | 0
IW13 | HVAC Pre | Adco | 0 | 2026-07-20 | 2026-07-21 | 2 | 0
IW13 | Plumbing Pre | Hays | Hays | 2026-07-20 | 2026-07-24 | 5 | 0
IW13 | Electrical Pre | Dave Kaler | 0 | 2026-07-20 | 2026-07-21 | 2 | 0
IW13 | Slab | 3C Concrete | 3C Concrete | 2026-07-27 | 2026-07-30 | 4 | 0
IW13 | Framing | Gerardo | 0 | 2026-07-31 | 2026-09-10 | 30 | 0
IW13 | Roofing | Rod Smith | 0 | 2026-09-11 | 2026-09-16 | 4 | 0
IW13 | Brick | Julio H | 0 | 2026-09-17 | 2026-10-14 | 20 | 0
IW13 | Stone | Julio H | 0 | 2026-09-17 | 2026-10-14 | 20 | 0
IW13 | Siding | Gerardo | 0 | 2026-09-17 | 2026-10-14 | 20 | 0
IW13 | Rough Grade | 0 | 0 | 2026-10-15 | 2026-10-16 | 2 | 0
IW13 | Irrigation | Ramiro | 0 | 2026-10-19 | 2026-10-20 | 2 | 0
IW13 | Finish Grade | Jacob Hayden | 0 | 2026-10-21 | 2026-10-22 | 2 | 0
IW13 | Landscaping | Jacob Hayden | 0 | 2026-10-21 | 2026-10-22 | 2 | 0
IW13 | Lawn Seeding | TruGreen | 0 | 2026-10-23 | 2026-10-26 | 2 | 0
IW13 | Gutter drains | 0 | 0 | 2026-10-19 | 2026-10-20 | 2 | 0
IW13 | HVAC Rough | Adco | 0 | 2026-09-11 | 2026-09-17 | 5 | 0
IW13 | Plumbing Rough | Hays | Hays | 2026-09-11 | 2026-09-17 | 5 | 0
IW13 | Electrical Rough | Dave Kaler | 0 | 2026-09-11 | 2026-09-24 | 10 | 0
IW13 | Insulation Walls | Tyler Champion | 0 | 2026-09-25 | 2026-09-28 | 2 | 0
IW13 | Sheetrock | Bernall Constr. | 0 | 2026-09-29 | 2026-10-19 | 15 | 0
IW13 | Painting Primer | L&L Painting | 0 | 2026-10-20 | 2026-10-22 | 3 | 0
IW13 | Garage Doors | Danny Liedecher | 0 | 2026-10-23 | 2026-10-26 | 2 | 0
IW13 | Flooring | LW Contracting | 0 | 2026-10-23 | 2026-10-29 | 5 | 0
IW13 | Tile Work | LW Contracting | 0 | 2026-10-23 | 2026-11-03 | 8 | 0
IW13 | Trim Interior | Matt Thorne | Matt Thorne | 2026-10-30 | 2026-11-26 | 20 | 0
IW13 | Trim Exterior | Matt Thorne | Matt Thorne | 2026-10-15 | 2026-10-16 | 2 | 0
IW13 | Cabinets | Whittmer | 0 | 2026-10-30 | 2026-11-03 | 3 | 0
IW13 | Countertops | Tate Granit | 0 | 2026-11-04 | 2026-11-05 | 2 | 0
IW13 | Painting Main | L&L Painting | 0 | 2026-11-06 | 2026-11-19 | 10 | 0
IW13 | Appliances | Dave Kaler | 0 | 2026-11-06 | 2026-11-09 | 2 | 0
IW13 | HVAC Finish | Adco | 0 | 2026-11-20 | 2026-11-23 | 2 | 0
IW13 | Plumbing Finish | Hays | Hays | 2026-11-06 | 2026-11-09 | 2 | 0
IW13 | Electrical Finish | Dave Kaler | 0 | 2026-11-20 | 2026-11-25 | 4 | 0
IW13 | Insulation Ceiling | Tyler Champion | 0 | 2026-11-26 | 2026-11-27 | 2 | 0
IW13 | Painting Finish | L&L Painting | 0 | 2026-11-26 | 2026-12-02 | 5 | 0
IW13 | Cleaning | Angies Cleaning | 0 | 2026-12-03 | 2026-12-07 | 3 | 0
IW14 | Estimate | Willett & Assoc. | 0 | 2026-06-24 | 2026-07-07 | 10 | 0
IW14 | Clearing | Willett & Assoc. | 0 | 2026-07-08 | 2026-07-10 | 3 | 0
IW14 | Site Prep | Willett & Assoc. | 0 | 2026-07-13 | 2026-07-14 | 2 | 0
IW14 | Footer | 3C Concrete | 3C Concrete | 2026-07-15 | 2026-07-20 | 4 | 0
IW14 | Block | Julio H | 0 | 2026-07-21 | 2026-08-03 | 10 | 0
IW14 | French Drain | Jacob Hayden | 0 | 2026-08-04 | 2026-08-05 | 2 | 0
IW14 | Insulation Block | Tyler Champion | 0 | 2026-08-04 | 2026-08-05 | 2 | 0
IW14 | Rock Work | 0 | 0 | 2026-08-06 | 2026-08-07 | 2 | 0
IW14 | HVAC Pre | Adco | 0 | 2026-08-10 | 2026-08-11 | 2 | 0
IW14 | Plumbing Pre | Hays | Hays | 2026-08-10 | 2026-08-14 | 5 | 0
IW14 | Electrical Pre | Dave Kaler | 0 | 2026-08-10 | 2026-08-11 | 2 | 0
IW14 | Slab | 3C Concrete | 3C Concrete | 2026-08-17 | 2026-08-20 | 4 | 0
IW14 | Framing | Gerardo | 0 | 2026-08-21 | 2026-10-01 | 30 | 0
IW14 | Roofing | Rod Smith | 0 | 2026-10-02 | 2026-10-07 | 4 | 0
IW14 | Brick | Julio H | 0 | 2026-10-08 | 2026-11-04 | 20 | 0
IW14 | Stone | Julio H | 0 | 2026-10-08 | 2026-11-04 | 20 | 0
IW14 | Siding | Gerardo | 0 | 2026-10-08 | 2026-11-04 | 20 | 0
IW14 | Rough Grade | 0 | 0 | 2026-11-05 | 2026-11-06 | 2 | 0
IW14 | Irrigation | Ramiro | 0 | 2026-11-09 | 2026-11-10 | 2 | 0
IW14 | Finish Grade | Jacob Hayden | 0 | 2026-11-11 | 2026-11-12 | 2 | 0
IW14 | Landscaping | Jacob Hayden | 0 | 2026-11-11 | 2026-11-12 | 2 | 0
IW14 | Lawn Seeding | TruGreen | 0 | 2026-11-13 | 2026-11-16 | 2 | 0
IW14 | Gutter drains | 0 | 0 | 2026-11-09 | 2026-11-10 | 2 | 0
IW14 | HVAC Rough | Adco | 0 | 2026-10-02 | 2026-10-08 | 5 | 0
IW14 | Plumbing Rough | Hays | Hays | 2026-10-02 | 2026-10-08 | 5 | 0
IW14 | Electrical Rough | Dave Kaler | 0 | 2026-10-02 | 2026-10-15 | 10 | 0
IW14 | Insulation Walls | Tyler Champion | 0 | 2026-10-16 | 2026-10-19 | 2 | 0
IW14 | Sheetrock | Bernall Constr. | 0 | 2026-10-20 | 2026-11-09 | 15 | 0
IW14 | Painting Primer | L&L Painting | 0 | 2026-11-10 | 2026-11-12 | 3 | 0
IW14 | Garage Doors | Danny Liedecher | 0 | 2026-11-13 | 2026-11-16 | 2 | 0
IW14 | Flooring | LW Contracting | 0 | 2026-11-13 | 2026-11-19 | 5 | 0
IW14 | Tile Work | LW Contracting | 0 | 2026-11-13 | 2026-11-24 | 8 | 0
IW14 | Trim Interior | Matt Thorne | Matt Thorne | 2026-11-20 | 2026-12-17 | 20 | 0
IW14 | Trim Exterior | Matt Thorne | Matt Thorne | 2026-11-05 | 2026-11-06 | 2 | 0
IW14 | Cabinets | Whittmer | 0 | 2026-11-20 | 2026-11-24 | 3 | 0
IW14 | Countertops | Tate Granit | 0 | 2026-11-25 | 2026-11-26 | 2 | 0
IW14 | Painting Main | L&L Painting | 0 | 2026-11-27 | 2026-12-10 | 10 | 0
IW14 | Appliances | Dave Kaler | 0 | 2026-11-27 | 2026-11-30 | 2 | 0
IW14 | HVAC Finish | Adco | 0 | 2026-12-11 | 2026-12-14 | 2 | 0
IW14 | Plumbing Finish | Hays | Hays | 2026-11-27 | 2026-11-30 | 2 | 0
IW14 | Electrical Finish | Dave Kaler | 0 | 2026-12-11 | 2026-12-16 | 4 | 0
IW14 | Insulation Ceiling | Tyler Champion | 0 | 2026-12-17 | 2026-12-18 | 2 | 0
IW14 | Painting Finish | L&L Painting | 0 | 2026-12-17 | 2026-12-23 | 5 | 0
IW14 | Cleaning | Angies Cleaning | 0 | 2026-12-24 | 2026-12-28 | 3 | 0
IW15 | Estimate | Willett & Assoc. | 0 | 2026-07-15 | 2026-07-28 | 10 | 0
IW15 | Clearing | Willett & Assoc. | 0 | 2026-07-29 | 2026-07-31 | 3 | 0
IW15 | Site Prep | Willett & Assoc. | 0 | 2026-08-03 | 2026-08-04 | 2 | 0
IW15 | Footer | 3C Concrete | 3C Concrete | 2026-08-05 | 2026-08-10 | 4 | 0
IW15 | Block | Julio H | 0 | 2026-08-11 | 2026-08-24 | 10 | 0
IW15 | French Drain | Jacob Hayden | 0 | 2026-08-25 | 2026-08-26 | 2 | 0
IW15 | Insulation Block | Tyler Champion | 0 | 2026-08-25 | 2026-08-26 | 2 | 0
IW15 | Rock Work | 0 | 0 | 2026-08-27 | 2026-08-28 | 2 | 0
IW15 | HVAC Pre | Adco | 0 | 2026-08-31 | 2026-09-01 | 2 | 0
IW15 | Plumbing Pre | Hays | Hays | 2026-08-31 | 2026-09-04 | 5 | 0
IW15 | Electrical Pre | Dave Kaler | 0 | 2026-08-31 | 2026-09-01 | 2 | 0
IW15 | Slab | 3C Concrete | 3C Concrete | 2026-09-07 | 2026-09-10 | 4 | 0
IW15 | Framing | Gerardo | 0 | 2026-09-11 | 2026-10-22 | 30 | 0
IW15 | Roofing | Rod Smith | 0 | 2026-10-23 | 2026-10-28 | 4 | 0
IW15 | Brick | Julio H | 0 | 2026-10-29 | 2026-11-25 | 20 | 0
IW15 | Stone | Julio H | 0 | 2026-10-29 | 2026-11-25 | 20 | 0
IW15 | Siding | Gerardo | 0 | 2026-10-29 | 2026-11-25 | 20 | 0
IW15 | Rough Grade | 0 | 0 | 2026-11-26 | 2026-11-27 | 2 | 0
IW15 | Irrigation | Ramiro | 0 | 2026-11-30 | 2026-12-01 | 2 | 0
IW15 | Finish Grade | Jacob Hayden | 0 | 2026-12-02 | 2026-12-03 | 2 | 0
IW15 | Landscaping | Jacob Hayden | 0 | 2026-12-02 | 2026-12-03 | 2 | 0
IW15 | Lawn Seeding | TruGreen | 0 | 2026-12-04 | 2026-12-07 | 2 | 0
IW15 | Gutter drains | 0 | 0 | 2026-11-30 | 2026-12-01 | 2 | 0
IW15 | HVAC Rough | Adco | 0 | 2026-10-23 | 2026-10-29 | 5 | 0
IW15 | Plumbing Rough | Hays | Hays | 2026-10-23 | 2026-10-29 | 5 | 0
IW15 | Electrical Rough | Dave Kaler | 0 | 2026-10-23 | 2026-11-05 | 10 | 0
IW15 | Insulation Walls | Tyler Champion | 0 | 2026-11-06 | 2026-11-09 | 2 | 0
IW15 | Sheetrock | Bernall Constr. | 0 | 2026-11-10 | 2026-11-30 | 15 | 0
IW15 | Painting Primer | L&L Painting | 0 | 2026-12-01 | 2026-12-03 | 3 | 0
IW15 | Garage Doors | Danny Liedecher | 0 | 2026-12-04 | 2026-12-07 | 2 | 0
IW15 | Flooring | LW Contracting | 0 | 2026-12-04 | 2026-12-10 | 5 | 0
IW15 | Tile Work | LW Contracting | 0 | 2026-12-04 | 2026-12-15 | 8 | 0
IW15 | Trim Interior | Matt Thorne | Matt Thorne | 2026-12-11 | 2027-01-07 | 20 | 0
IW15 | Trim Exterior | Matt Thorne | Matt Thorne | 2026-11-26 | 2026-11-27 | 2 | 0
IW15 | Cabinets | Whittmer | 0 | 2026-12-11 | 2026-12-15 | 3 | 0
IW15 | Countertops | Tate Granit | 0 | 2026-12-16 | 2026-12-17 | 2 | 0
IW15 | Painting Main | L&L Painting | 0 | 2026-12-18 | 2026-12-31 | 10 | 0
IW15 | Appliances | Dave Kaler | 0 | 2026-12-18 | 2026-12-21 | 2 | 0
IW15 | HVAC Finish | Adco | 0 | 2027-01-01 | 2027-01-04 | 2 | 0
IW15 | Plumbing Finish | Hays | Hays | 2026-12-18 | 2026-12-21 | 2 | 0
IW15 | Electrical Finish | Dave Kaler | 0 | 2027-01-01 | 2027-01-06 | 4 | 0
IW15 | Insulation Ceiling | Tyler Champion | 0 | 2027-01-07 | 2027-01-08 | 2 | 0
IW15 | Painting Finish | L&L Painting | 0 | 2027-01-07 | 2027-01-13 | 5 | 0
IW15 | Cleaning | Angies Cleaning | 0 | 2027-01-14 | 2027-01-18 | 3 | 0

## Bottleneck Load
Bottleneck Vendor | Capacity | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06
3C Concrete | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hays | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Matt Thorne | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2