## KEY
Projects | Sub Color | Subcontractors | Scope 1 | Scope 2 | Scope 3 | Scope 4 | Scope 5 | Scope 6 | Scope 7
1 |  | 3C Concrete | Footer | Slab | Driveway
2 |  | Willett & Assoc. | Estimate | Clearing | Site Prep | Rough grade | Rock work
3 |  | Julio H | Block | Brick | Stone
4 |  | Gerardo | Framing | Siding
|  | Rod Smith | Roofing
|  | Dave Kaler | Electrical Pre | Electrical Rough | Electrical Finish | Appliances
|  | Adco | HVAC Pre | HVAC Rough | HVAC Finish
|  | Hays | Plumbing Pre | Plumbing Rough | Plumbing Finish
|  | LW Contracting | Flooring | Tile Work
|  | Tyler Champion | Insulation Block | Insulation Walls | Insulation Ceiling
|  | Bernall Constr. | Sheetrock
|  | Danny Liedecher | Garage Doors
|  | BlueGrass Gutters | Gutters
|  | Matt Thorn | Trim Interior | Trim Exterior
|  | L&L Painting | Painting Primer | Painting Main | Painting Finish
|  | Whittmer | Cabinets
|  | Tate Granit | Countertops
|  | Angie Mullens | Closets
|  | Jacob Hayden | Landscaping | Finish Grade | French Drain | Gutter Drains
|  | Ramiro | Irrigation
|  | TruGreen | Lawn Seeding
|  | Angies Cleaning | Cleaning

## Gantt
[7 empty] | 2026-04-05 | [6 empty] | 2026-04-12 | [6 empty] | 2026-04-19 | [6 empty] | 2026-04-26 | [6 empty] | 2026-05-03 | [6 empty] | 2026-05-10 | [6 empty] | 2026-05-17 | [6 empty] | 2026-05-24 | [6 empty] | 2026-05-31 | [6 empty] | 2026-06-07 | [6 empty] | 2026-06-14 | [6 empty] | 2026-06-21 | [6 empty] | 2026-06-28 | [6 empty] | 2026-07-05 | [6 empty] | 2026-07-12 | [6 empty] | 2026-07-19 | [6 empty] | 2026-07-26 | [6 empty] | 2026-08-02 | [6 empty] | 2026-08-09 | [6 empty] | 2026-08-16 | [6 empty] | 2026-08-23 | [6 empty] | 2026-08-30 | [6 empty] | 2026-09-06 | [6 empty] | 2026-09-13 | [6 empty] | 2026-09-20 | [6 empty] | 2026-09-27 | [6 empty] | 2026-10-04 | [6 empty] | 2026-10-11 | [6 empty] | 2026-10-18 | [6 empty] | 2026-10-25 | [6 empty] | 2026-11-01 | [6 empty] | 2026-11-08 | [6 empty] | 2026-11-15 | [6 empty] | 2026-11-22 | [6 empty] | 2026-11-29 | [6 empty] | 2026-12-06 | [6 empty] | 2026-12-13 | [6 empty] | 2026-12-20 | [6 empty] | 2026-12-27 | [6 empty] | 2027-01-03 | [6 empty] | 2027-01-10 | [6 empty] | 2027-01-17 | [6 empty] | 2027-01-24 | [6 empty] | 2027-01-31 | [6 empty] | 2027-02-07 | [6 empty] | 2027-02-14 | [6 empty] | 2027-02-21 | [6 empty] | 2027-02-28 | [6 empty] | 2027-03-07 | [6 empty] | 2027-03-14 | [6 empty] | 2027-03-21
|  |  |  | Days |  |  | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S | M | T | W | TH | F | S | S
Project | Subcontractor | Scope | Start Date | To Complete | End Date | Dependancy | time axis 2026-03-30 to 2027-03-21
IW10 | Willett & Assoc. | Estimate | 2026-04-01 | 10 | 2026-04-14
| Willett & Assoc. | Clearing | 2026-04-15 | 3 | 2026-04-17 | Estimate
| Willett & Assoc. | Site Prep | 2026-04-18 | 2 | 2026-04-20 | Clearing
| 3C Concrete | Footer | 2026-04-21 | 4 | 2026-04-24 | Site Prep
| Julio H | Block | 2026-04-25 | 6 | 2026-05-01 | Footer
| Jacob Hayden | French Drain | 2026-05-02 | 2 | 2026-05-04 | Block
| Tyler Champion | Insulation Block | 2026-05-02 | 2 | 2026-05-04 | Block
| Willett & Assoc. | Rock Work | 2026-05-05 | 2 | 2026-05-06 | Insulation Block
| Adco | HVAC Pre | 2026-05-07 | 2 | 2026-05-08 | Rock Work
| Hays | Plumbing Pre | 2026-05-07 | 5 | 2026-05-13 | Rock Work
| Dave Kaler | Electrical Pre | 2026-05-07 | 2 | 2026-05-08 | Rock Work
| 3C Concrete | Slab | 2026-05-14 | 3 | 2026-05-18 | Plumbing Pre
| Gerardo | Framing | 2026-05-19 | 30 | 2026-06-29 | Slab
| Rod Smith | Roofing | 2026-06-30 | 3 | 2026-07-02 | Framing
| Julio H | Brick | 2026-06-30 | 20 | 2026-07-27 | Framing
| Julio H | Stone | 2026-06-30 | 20 | 2026-07-27 | Framing
| Gerardo | Siding | 2026-06-30 | 10 | 2026-07-13 | Framing
| Willett & Assoc. | Rough Grade | 2026-07-28 | 2 | 2026-07-29 | Brick
| Ramiro | Irrigation | 2026-07-30 | 2 | 2026-07-31 | Rough Grade
| Jacob Hayden | Finish Grade | 2026-08-01 | 2 | 2026-08-03 | Irrigation
| Jacob Hayden | Landscaping | 2026-08-01 | 2 | 2026-08-03 | Irrigation
| TruGreen | Lawn Seeding | 2026-08-04 | 2 | 2026-08-05 | Finish Grade
| Jacob Hayden | Gutter drains | 2026-07-30 | 2 | 2026-07-31 | Rough Grade
| Adco | HVAC Rough | 2026-06-30 | 5 | 2026-07-06 | Framing
| Hays | Plumbing Rough | 2026-06-30 | 5 | 2026-07-06 | Framing
| Dave Kaler | Electrical Rough | 2026-06-30 | 10 | 2026-07-13 | Framing
| Tyler Champion | Insulation Walls | 2026-07-14 | 2 | 2026-07-15 | Electrical Rough
| Bernall Constr. | Sheetrock | 2026-07-16 | 10 | 2026-07-29 | Insulation Walls
| L&L Painting | Painting Primer | 2026-07-30 | 3 | 2026-08-03 | Sheetrock
| Danny Liedecher | Garage Doors | 2026-08-04 | 2 | 2026-08-05 | Painting Primer
| LW Contracting | Flooring | 2026-08-04 | 5 | 2026-08-10 | Painting Primer
| LW Contracting | Tile Work | 2026-08-04 | 8 | 2026-08-13 | Painting Primer
| Matt Thorn | Trim Interior | 2026-08-11 | 20 | 2026-09-07 | Flooring
| Matt Thorn | Trim Exterior | 2026-07-14 | 2 | 2026-07-15 | Siding
| Whittmer | Cabinets | 2026-08-11 | 3 | 2026-08-13 | Flooring
| Tate Granit | Countertops | 2026-08-14 | 2 | 2026-08-17 | Cabinets
| L&L Painting | Painting Main | 2026-08-18 | 10 | 2026-08-31 | Countertops
| Dave Kaler | Appliances | 2026-08-18 | 2 | 2026-08-19 | Countertops
| Adco | HVAC Finish | 2026-09-01 | 2 | 2026-09-02 | Painting Main
| Hays | Plumbing Finish | 2026-08-18 | 2 | 2026-08-19 | Countertops
| Dave Kaler | Electrical Finish | 2026-09-01 | 4 | 2026-09-04 | Painting Main
| Tyler Champion | Insulation Ceiling | 2026-09-05 | 2 | 2026-09-07 | Electrical Finish
| L&L Painting | Painting Finish | 2026-09-05 | 5 | 2026-09-10 | Electrical Finish
| Angies Cleaning | Cleaning | 2026-09-11 | 3 | 2026-09-15 | Painting Finish
|  |  |  | 167 | Estimate to cleaning
|  |  |  | 153 | Days to build
|  |  |  | 5.0312 | Months to build